## Goals
ID | Goal | Subteam | Status | Success Metric | Notes
GE_M001 | Win Endurance | General | On Track | Get Lapsim data on needed power limit, regen strategy
GE_M002 | Win Design | General | On Track
GE_M003 | Win Cost | General | On Track
GE_M004 | Win Presentation | General | On Track
PT_M001 | Proper Mounting + Integration | Powertrain | On Track | Robust with a consistent safety factor, no tapes,
CH_M001 | Reliable Car | Chassis | Delayed | Elaborate
CH_M002 | 380 LB Car | Chassis | Delayed | Need Lapsim data on this
MO_M001 | 40lb Tub | Monocoque | On Track
ER_M001 | Full Working/Rules Compliant Sensor Package | Ergonomics | On Track
MO_M002 | Testing: 95% of Elastic Modulus of Steel | Monocoque | On Track
HV_M001 | 90lb pack | High Voltage | On Track
GE_M005 | Stay Competitive in all events | General | On Track
AU_M001 | Complete Full Trackdrive | Autonomy | On Track
AU_M002 | System that can support human driving speeds | Autonomy | On Track
AU_M003 | Seamless integration with ARG26 & safety-compliant | Autonomy | On Track
ER_M002 | Accurately redefine driver load cases across all parts | Ergonomics | On Track | Have the Data to backup our load cases, hasn't been done in years.
LV_M001 | Commonized components | Low Voltage | On Track | Altium library created and integrated into all PCB designs

## Slack Users (hidden)
Name in Sheet | Slack User ID

## Slack Channels (hidden)
Subteam | Slack Channel ID

## Bot Log (hidden)
Timestamp | Level | Run Date | Milestone | Subteam | Event | Dedupe Key | Details | Slack Message ID
2026-08-31 14:40 | INFO | 2026-08-31 |  |  | RUN_STARTED |  | Daily milestone bot started. Dry run: true.
2026-08-31 14:40 | ERROR | 2026-08-31 | PT_M001 |  | INVALID_MILESTONE_DUE |  | Milestone PT_M001 has no valid Due date.
2026-08-31 14:40 | ERROR | 2026-08-31 | PT_M003 |  | INVALID_MILESTONE_DUE |  | Milestone PT_M003 has no valid Due date.
2026-08-31 14:40 | ERROR | 2026-08-31 | PT_M004 |  | INVALID_MILESTONE_DUE |  | Milestone PT_M004 has no valid Due date.
2026-08-31 14:40 | ERROR | 2026-08-31 | PT_M005 |  | INVALID_MILESTONE_DUE |  | Milestone PT_M005 has no valid Due date.
2026-08-31 14:40 | ERROR | 2026-08-31 | GE_M008 |  | INVALID_MILESTONE_DUE |  | Milestone GE_M008 has no valid Due date.
2026-08-31 14:40 | ERROR | 2026-08-31 | GE_M009 |  | INVALID_MILESTONE_DUE |  | Milestone GE_M009 has no valid Due date.
2026-08-31 14:40 | ERROR | 2026-08-31 | FW_M001 |  | INVALID_MILESTONE_DUE |  | Milestone FW_M001 has no valid Due date.
2026-08-31 14:40 | ERROR | 2026-08-31 | MO_M005 |  | INVALID_MILESTONE_DUE |  | Milestone MO_M005 has no valid Due date.
2026-08-31 14:40 | ERROR | 2026-08-31 | MO_M006 |  | INVALID_MILESTONE_DUE |  | Milestone MO_M006 has no valid Due date.
2026-08-31 14:40 | ERROR | 2026-08-31 | MO_M009 |  | INVALID_MILESTONE_DUE |  | Milestone MO_M009 has no valid Due date.
2026-08-31 14:40 | ERROR | 2026-08-31 | AE_M001 |  | INVALID_MILESTONE_DUE |  | Milestone AE_M001 has no valid Due date.
2026-08-31 14:40 | ERROR | 2026-08-31 | AE_M002 |  | INVALID_MILESTONE_DUE |  | Milestone AE_M002 has no valid Due date.
2026-08-31 14:40 | ERROR | 2026-08-31 | AE_M003 |  | INVALID_MILESTONE_DUE |  | Milestone AE_M003 has no valid Due date.
2026-08-31 14:40 | ERROR | 2026-08-31 | AE_M004 |  | INVALID_MILESTONE_DUE |  | Milestone AE_M004 has no valid Due date.
2026-08-31 14:40 | ERROR | 2026-08-31 | LV_M001 |  | INVALID_MILESTONE_DUE |  | Milestone LV_M001 has no valid Due date.
2026-08-31 14:40 | ERROR | 2026-08-31 | FW_M003 |  | INVALID_MILESTONE_DUE |  | Milestone FW_M003 has no valid Due date.
2026-08-31 14:40 | INFO | 2026-08-31 | HV_M001 |  | NO_MILESTONE_TASKS |  | No tasks in Task Master reference milestone HV_M001.
2026-08-31 14:40 | INFO | 2026-08-31 | SU_M010 |  | NO_MILESTONE_TASKS |  | No tasks in Task Master reference milestone SU_M010.
2026-08-31 14:40 | INFO | 2026-08-31 | GE_M010 |  | NO_MILESTONE_TASKS |  | No tasks in Task Master reference milestone GE_M010.
2026-08-31 14:40 | INFO | 2026-08-31 |  |  | RUN_COMPLETED |  | Processed 3 triggered milestone(s).

## Milestones
ID | Task | Subteam | Start | Due | Status | Dependencies | Notes
GE_M001 | First Drive | General |  | 2027-02-07 | Not Started
CH_M001 | Chassis Drop | Chassis |  | 2027-01-25 | Not Started
PT_M001 | Powertrain Off Car Drop | Powertrain |  |  | Not Started
GE_M002 | SDR | General |  | 2026-08-16 | Complete
GE_M003 | System PDR | General |  | 2026-09-14 | In Progress |  | System Level Targets, reviewed by Alumni
GE_M004 | PDR | General |  | 2026-09-28 | Not Started
GE_M005 | ADR | General |  | 2026-10-25 | Not Started
GE_M006 | FDR | General |  | 2026-11-25 | Not Started
PT_M002 | Order DTI Motors + Inverters | Powertrain |  | 2026-08-01 | Blocked
PT_M003 | Motor Spin | Powertrain |  |  | Not Started
PT_M004 | Motor Spin on Car | Powertrain |  |  | Not Started
PT_M005 | Steady State Powertrain | Powertrain |  |  | Not Started
GE_M007 | CAD Freeze | General |  | 2026-10-22 | Not Started
GE_M008 | Rules Released | General |  |  | Not Started
CH_M002 | Dynamic Cad done | Chassis |  | 2026-10-19 | Not Started
HV_M001 | Order pouch cells | High Voltage |  | 2026-08-30 | Not Started
HV_M002 | Order fireproof composite material | High Voltage |  | 2026-08-18 | Not Started
HV_M003 | Module parts manufactured and QCed | High Voltage |  | 2026-12-01 | Not Started
HV_M004 | Composite case manufactured | High Voltage |  | 2026-12-01 | Not Started
HV_M005 | Acc electronics components finalized (busbars inclusive) | High Voltage |  | 2026-09-21 | Not Started
AU_M001 | Autonomous Sensor + ARG26 Trackdrive | Autonomy |  | 2026-10-17 | Not Started
AU_M002 | Mapping + ARG26 Trackdrive | Autonomy |  | 2026-11-30 | Not Started
AU_M003 | Integration of DV + ARG26 | Autonomy |  | 2027-02-22 | Not Started
AU_M004 | First driverless motion through set of cones | Autonomy |  | 2027-03-08 | Not Started
AU_M005 | First full driverless autox | Autonomy |  | 2027-04-05 | Not Started
AU_M006 | Furst full driverless trackdrive | Autonomy |  | 2027-05-12 | Not Started
CO_M001 | Liquid Loop Assembled on Bench | Cooling |  | 2027-01-15 | Not Started
CO_M002 | Liquid Loop Bled on Car | Cooling |  | 2027-01-26 | Not Started
CO_M003 | Final Loop Test | Cooling |  | 2027-01-20 | Not Started
CO_M004 | Final Designs Manufactured | Cooling |  | 2027-01-13 | Not Started
CO_M005 | Final Designs Completed | Cooling |  | 2026-12-11 | Not Started
CO_M006 | Full Prototype Loop Test | Cooling |  | 2026-10-17 | Not Started
CO_M007 | Full Prototype Manufactured | Cooling |  | 2026-10-10 | Not Started
CO_M008 | Full Prototype Designs Completed | Cooling |  | 2026-09-26 | Not Started
CO_M009 | Cooling Power Requirements | Cooling |  | 2026-09-19 | Not Started
CO_M010 | Heat Rejection and Pressure Drop Targets | Cooling |  | 2026-09-11 | Not Started
CO_M011 | Liquid Loop Simulation Running | Cooling |  | 2026-09-01 | Not Started
SU_M001 | Finalize Tire Choice | Suspension |  | 2026-09-06 | Not Started |  | Recheck tire data
SU_M002 | Points Finalized | Suspension |  | 2026-09-15 | Not Started
SU_M003 | Link Loads Finalized | Suspension |  | 2026-09-28 | Not Started
SU_M004 | Finalize ARB stifness | Suspension |  | 2026-09-28 | Not Started
SU_M005 | Finalize Rates | Suspension |  | 2026-09-28 | Not Started
SU_M006 | Finalize WB, Front and Rear TWs, Ride Height, Weight Distribution, CG Height, Vehicle/Driver/Sprung Weights | Suspension |  | 2026-09-06 | Not Started |  | Does this depend on driver selection?
SU_M007 | Suspension Assembled on Car | Suspension |  | 2027-01-24 | Not Started
SU_M008 | Suspension PDR drafts done | Suspension |  | 2026-09-21 | Not Started
SU_M009 | Finalize Suspension Weight Budget | Suspension |  | 2026-09-01 | Not Started
SU_M010 | Ready to Analyze and Interpret Car Data | Suspension |  | 2026-08-30 | Not Started |  | Compile list of ARG26 sensors and how interpret
GE_M009 | Finalize Drivers | General |  |  | In Progress
FW_M001 | ARG26 VD Working and Tunable | Firmware |  |  | Not Started
HV_M006 | Finalize composite TB container ply schedule per SES | High Voltage |  | 2026-10-01 | Not Started
HV_M007 | Tractive Battery electrical architechture finalized | High Voltage |  | 2026-08-26 | Not Started
HV_M008 | Laser Welder Installed in Autolab | High Voltage |  | 2026-09-01 | Not Started
HV_M009 | Tractive Battery + Inverter Packaging finalized | High Voltage |  | 2026-09-15 | Not Started
HV_M010 | Pack active cooling math finalized | High Voltage |  | 2026-09-01 | Not Started
HV_M011 | Module Discharge Rig Assembled | High Voltage |  | 2026-09-07 | Not Started
HV_M012 | Active cooling validated with module discharge rig | High Voltage |  | 2026-09-09 | Not Started
HV_M013 | Tractive Battery Modules + Container SES done | High Voltage |  | 2026-11-01 | Not Started
MO_M001 | Order Carbon for Monocoque | Monocoque |  | 2026-07-08 | Complete
MO_M002 | All Monocoque Material Ordered | Monocoque |  | 2026-08-14 | In Progress
MO_M003 | Have All Carbon (latest) | Monocoque |  | 2026-09-07 | In Progress
MO_M004 | Update and lock CAD drill point (MAY CHANGE) | Monocoque |  | 2026-10-19 | Not Started |  | dependent on susp and other subteams
MO_M005 | Holes Drilled into Plug | Monocoque |  |  | Not Started
MO_M006 | Plug Post Processed | Monocoque |  |  | Not Started
MO_M007 | Finish releasing one mold | Monocoque |  | 2026-11-19 | Not Started
GE_M010 | ARG26 First Drive | General |  | 2026-09-05 | Not Started
MO_M008 | Ply schedules FROZEN | Monocoque |  | 2026-11-20 | Not Started
MO_M009 | SES Submitted | Monocoque |  |  | Not Started
MO_M010 | Monocoque Drop | Monocoque |  | 2027-01-18 | Not Started
AU_M007 | Sensors and Compute Ordered | Autonomy |  | 2026-09-29 | Blocked
GE_M011 | ARG27 Second Drive | General |  | 2027-03-14 | Not Started
GE_M012 | Fully rules compliant car | General |  | 2027-04-01 | Blocked
AE_M001 | CFD Freeze | Aerodynamics |  |  | Not Started
AE_M002 | Finalize Aero Targets | Aerodynamics |  |  | In Progress
AE_M003 | Plugs and Tooling Made | Aerodynamics |  |  | Not Started
AE_M004 | Mounted to car | Aerodynamics |  |  | Not Started
ER_M001 | Ergo Points Finalized | Ergonomics |  | 2026-09-30 | Not Started
LV_M001 | Altium library groundwork finished | Low Voltage |  |  | In Progress
LV_M002 | First revs schematics done | Low Voltage |  | 2026-08-17 | In Progress
LV_M003 | First revs layout done | Low Voltage |  | 2026-09-09 | Not Started
LV_M004 | First revs ordered | Low Voltage |  | 2026-09-10 | Not Started
LV_M005 | First revs tested | Low Voltage |  | 2026-09-28 | Not Started |  | PDR
LV_M006 | Precharge tested in loop | Low Voltage |  | 2027-01-07 | Not Started
LV_M007 | BMS Children LV/HV tested | Low Voltage |  | 2027-01-08 | Not Started
LV_M008 | BMS Children integrated onto modules | Low Voltage |  | 2027-01-09 | Not Started
LV_M009 | Shutdown circuit closed | Low Voltage |  | 2027-01-15 | Not Started
LV_M010 | LV Harness ICDs finished | Low Voltage |  | 2026-10-11 | Not Started
LV_M011 | Enclosures finalized | Low Voltage |  | 2026-10-22 | Not Started |  | depends on cad freeze?
LV_M012 | Power budget estimated | Low Voltage |  | 2026-10-01 | Not Started
LV_M013 | LV Harness Sensors finalized | Low Voltage |  | 2026-10-11 | Not Started
ER_M002 | Steering System Components Ordered | Ergonomics |  | 2026-11-13 | Not Started
ER_M003 | All Driver Loads Redefined | Ergonomics |  | 2026-09-18 | Not Started
CO_M012 | Mock Endurance ARG26 | Cooling | 2026-08-31 | 2026-09-04 | Not Started |  | Full-system Cooling validation during mock endurance
CO_M013 | Liquid Loop Installed on Car | Cooling | 2027-01-15 | 2027-01-22 | Not Started |  | Final liquid loop assembled and integrated onto vehicle
ER_M004 | Mock Cockpit Template Passed | Ergonomics | 2027-02-01 | 2027-02-12 | Not Started |  | High-level validation of completed cockpit/ergonomics package
FW_M002 | ARG26 VD Fully Tested | Firmware |  | 2026-10-25 | Not Started |  | Due date is ADR; high-level validation of active vehicle dynamics controls
FW_M003 | BMS Code Validated | Firmware |  |  | Not Started |  | High-level validation milestone for BMS firmware
MO_M011 | Molds Complete and SES Submission Confirmed | Monocoque | 2026-12-06 | 2026-12-06 | Not Started |  | Major tooling/SES readiness milestone
MO_M012 | Monocoque Released from Molds | Monocoque | 2027-01-18 | 2027-01-18 | Not Started |  | Completed manufactured monocoque released from tooling
MO_M013 | Chassis Integration Complete | Monocoque | 2027-01-29 | 2027-01-29 | Not Started |  | Chassis integration complete
MO_M014 | Rolling Chassis | Monocoque | 2027-02-04 | 2027-02-04 | Not Started |  | Tentative; timing may depend on another subteam
MO_M015 | First Drive | Monocoque | 2027-02-14 | 2027-02-14 | Not Started |  | Vehicle achieves first drive
SU_M011 | First Suspension Assembly | Suspension | 2027-01-18 | 2027-01-21 | Not Started |  | Major subteam-level milestone representing first complete suspension assembly
BU_M001 | Upperclassman Apps Due | Business |  | 2026-09-01 | In Progress
BU_M002 | Upperclassman Offer | Business |  | 2026-09-16
BU_M003 | First Year Offer | Business |  | 2026-11-02
GE_M013 | Autolab Clean Up | General |  | 8/

## References (hidden)
Subteam | ID | Status | Priority | Assemblies
General | GE | Not Started | Critical | A00 - General
Chassis | CH | In Progress | High | A01 - Chassis
Powertrain | PT | Blocked | Medium | A02 - Powertrain
High Voltage | HV | Review | Low | A01 - High Voltage
Low Voltage | LV | Complete |  | A02 - Modules
Cooling | CO |  |  | A03 - Case
Firmware | FW |  |  | A04 - Accumulator Electronics
Autonomy | AU |  |  | A05 - Inverter Enclosure
Aerodynamics | AE |  |  | A06 - Powerhouse
Ergonomics | ER |  |  | A07 - Control Panel
Monocoque | MO |  |  | A08 - RTML and TSSI
Suspension | SU |  |  | A09 - Other High Voltage
Unsprung | UN |  |  | A01 - Low Voltage
Business | BU |  |  | A02 - Harness
A03 - ECU
A04 - BMS Child
A05 - ACU
A06 - Shutdown
A07 - Discharge
A08 - PDU
A09 - Dash
A10 - Other Low Voltage
A01 - Cooling
A02 - Liquid Loop
A03 - Cooling Sleeve
A04 - Accumulator Cooling
A05 - Other Cooling
A01 - Firmware
A02 - BMS Code
A03 - ECU Code
A04 - Active VD Controls
A05 - Dash Firmware
A06 - Other Firmware
A01 - Autonomy
A02 - Autonomy Mechanical
A03 - Path Planning and Following
A04 - Sensors and Harnessing
A05 - Compute and Hardware
A06 - Perception and Data Interface
A07 - Software Pipeline
A08 - Other Autonomy
A01 - Aerodynamics
A02 - Front Wing
A03 - Rear Wing
A04 - Undertray
A05 - Auxiliary Elements
A06 - Sidepod
A07 - CFD
A08 - Other Aerodynamics
A01 - Ergonomics
A02 - Steering
A03 - Pedals
A04 - Seat
A05 - Firewall
A06 - Head Restraint
A07 - Steering Wheel
A08 - Other Ergonomics
A01 - Monocoque
A02 - MO Geometry
A03 - Protective Structures
A05 - SES and Ply Schedules
A06 - Other Monocoque
A01 - Suspension
A02 - Links
A03 - Clevises
A04 - Rockers
A05 - Anti-Roll
A08 - Jig Plate
A09 - Other Suspension
A01 - Unsprung
A02 - Hubs and Uprights
A03 - Brakes
A04 - Gearbox
A05 - Other Unsprung
A01 - Business
A02 - Purchasing
A03 - Recruitment
A04 - Business Presentations
A05 - Fundraising, Sponsors
A06 - Website
A07 - Social Media
A08 - Merch
A09 - Other Business

## Task Master (hidden)
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
GE_A00_T001 | Subteam part designer sprints | General | 2026-08-31 | 2026-09-04 | In Progress |  |  | High |  |  |  | A00 - General
GE_A00_T002 | Tuning for Toronto Shootout | General | 2026-09-21 | 2026-09-30 | Not Started |  | Caroline Moskal | High |  |  |  | A00 - General
GE_A00_T003 | Pack for Toronto Shootout | General | 2026-10-01 | 2026-10-02 | Not Started |  | Caroline Moskal | High |  |  |  | A00 - General
GE_A00_T004 | Tech inspection for Toronto Shootout | General | 2026-09-28 | 2026-09-30 | Not Started |  | Caroline Moskal | High | GE_A00_T002 |  |  | A00 - General
GE_A01_T001 | Mech Check outs for ARG26 | Chassis | 2026-08-30 | 2026-09-01 | Complete |  | Nicholas Gavalas | High |  |  |  | A01 - Chassis
GE_A01_T002 | ARG26 Bolt Check | Chassis | 2026-08-30 | 2026-08-31 | In Progress |  | Nicholas Gavalas | High |  |  |  | A01 - Chassis
GE_A02_T001 | EV Check outs for ARG26 | Powertrain | 2026-08-31 | 2026-09-02 | Not Started |  | Will Hutter | High | GE_A01_T002 |  |  | A02 - Powertrain
GE_A02_T002 | Sensor integration on ARG26 | Powertrain | 2026-09-01 | 2026-09-05 | Not Started |  | Will Hutter | High |  |  |  | A02 - Powertrain
GE_A02_T003 | Charging ARG26 pack | Powertrain | 2026-09-02 | 2026-09-04 | Complete |  | Will Hutter | High |  |  |  | A02 - Powertrain
HV_A01_T001 | test task | High Voltage | [9 empty] | A01 - High Voltage
LV_A01_T001 | Altium library basics finished | Low Voltage | 2026-07-13 | 2026-08-09 | Review |  | Arielle Huang | High |  | Commonized components |  | A01 - Low Voltage
LV_A04_T001 | Design first rev of BMS Child | Low Voltage | 2026-08-01 | 2026-09-01 | In Progress |  | Sam Hunter | High |  | PCB ordered |  | A04 - BMS Child
LV_A04_T002 | Test/debug first rev of BMS child | Low Voltage | 2026-09-07 | 2026-09-21 | Not Started |  | Sam Hunter | High |  | Test report/results + required modifications | Dependent on LV006, couldn't select it | A04 - BMS Child
LV_A04_T003 | Validate communication between BMS child/mother | Low Voltage | 2026-09-21 | 2026-10-01 | Not Started |  | Sam Hunter | High |  | Functional basic BSM system | Timeline dependent on LV007, couldn't select it. Also Natsu is a co-owner, couldn't add him. | A04 - BMS Child
LV_A04_T004 | Design final rev of BMS child for module integration | Low Voltage | 2026-10-01 | 2026-11-16 | Not Started |  | Sam Hunter | High |  | PCB ordered | Dependent on LV008 | A04 - BMS Child
LV_A04_T005 | Test final rev of BMS child | Low Voltage | 2026-11-23 | 2026-12-01 | Not Started |  | Sam Hunter | High |  | Functioning child board | Dependent on LV009 | A04 - BMS Child
LV_A04_T006 | Bring up + validate all BMS children + spares | Low Voltage | 2026-12-01 | 2027-01-15 | Not Started |  | Sam Hunter | High |  | Working BMS system | Dependent on LV010 | A04 - BMS Child
LV_A06_T001 | Shutdown circuit closes | Low Voltage |  |  | Not Started |  | Arielle Huang Valerie Shu |  |  |  |  | A06 - Shutdown
LV_A07_T001 | Precharge and discharge validated | Low Voltage |  |  | Not Started |  | Arielle Huang Nathaniel Su |  |  |  |  | A07 - Discharge
LV_A08_T001 | Get PDM08 and ACC3s | Low Voltage | 2026-08-09 | 2026-09-07 | Not Started | [6 empty] | A08 - PDU
LV_A08_T002 | HV DCDC/LV DCDC Choice | Low Voltage |  |  | In Progress |  | Arielle Huang Sean Li |  |  | HV DCDC locked | For PDU, depends on cooling | A08 - PDU
LV_A08_T003 | Design first rev of PDU | Low Voltage | 2026-08-05 | 2026-09-05 | Not Started |  | Sean Li | High |  | PCB ordered | dependent on cooling pump/radiator/fan selection | A08 - PDU
LV_A09_T001 | Dash multple screens | Low Voltage |  |  | Not Started |  | Yifan Li Keira Chen |  |  |  |  | A09 - Dash
LV_A09_T002 | Design first rev of Dash | Low Voltage |  |  | Planned |  | Keira Chen | Medium |  | PCB ordered |  | A09 - Dash
LV_A09_T003 | Order Dash components | Low Voltage |  |  | Not Started |  | Keira Chen | Medium |  | components arrive |  | A09 - Dash
LV_A09_T004 | Bring up + Test Dash rev1 | Low Voltage |  |  | Not Started |  | Keira Chen | Medium |  | working Dash board |  | A09 - Dash
LV_A09_T005 | Dash harnessing | Low Voltage |  |  | Not Started |  | Keira Chen | Medium |  | harness is complete |  | A09 - Dash
LV_A09_T006 | Dash integration | Low Voltage |  |  | Not Started |  | Keira Chen | Medium |  | dash is on car and working |  | A09 - Dash
LV_A09_T007 | Bring up final rev Dash spares | Low Voltage |  |  | Not Started |  | Keira Chen | Medium |  | spares are available |  | A09 - Dash
CO_A02_T002 | Run full liquid loop pressure drop test | Cooling |  |  | Not Started |  | Ilana Yousuf | Medium |  |  |  | A02 - Liquid Loop
CO_A02_T009 | Identify system parameters w/ hand calcs and data |  |  |  | Not Started |  | Ilana Yousuf | High |  |  |  | A02 - Liquid Loop
CO_A02_T003 | Determine necessary radiator and fan specifications | Cooling | 2026-09-08 | 2026-09-11 | Not Started |  | Ilana Yousuf | High |  |  |  | A02 - Liquid Loop
CO_A02_T004 | Order stock radiator for testing | Cooling | 2026-09-15 | 2026-09-20 | Not Started |  | Ilana Yousuf | Medium |  |  |  | A02 - Liquid Loop
CO_A02_T005 | Test and confirm geometry/layout | Cooling | 2026-09-15 | 2026-09-25 | Not Started |  | Ilana Yousuf | Medium |  |  |  | A02 - Liquid Loop
CO_A02_T001 | PRIORITY: order custom radiator | Cooling | 2026-09-11 | 2026-09-30 | Not Started |  | Ilana Yousuf | High |  |  |  | A02 - Liquid Loop
CO_A02_T006 | Manufacture liquid loop prototype | Cooling | 2026-10-01 | 2026-10-08 | Not Started |  | Ilana Yousuf | Medium |  |  |  | A02 - Liquid Loop
CO_A02_T007 | Conduct tests and collect data for pressure drop and heat rejection | Cooling | 2026-10-10 | 2026-10-17 | Not Started |  | Ilana Yousuf | High |  |  |  | A02 - Liquid Loop
CO_A02_T008 | Assemble final liquid loop on bench | Cooling | 2027-01-04 | 2027-01-15 | Not Started |  | Ilana Yousuf | High |  |  |  | A02 - Liquid Loop
CO_A02_T010 | Calibrate Temp sensors and put on car for endurance testing | Cooling | 2026-09-04 | 2026-09-04 | Not Started |  |  | High |  |  |  | A02 - Liquid Loop
CO_A03_T001 | Run motor sleeve heat rejection + flow test | Cooling |  |  |  |  | Usanbolor Amartuvshin | Medium |  |  |  | A03 - Cooling Sleeve
CO_A03_T002 | Cooling Sleeve ANSYS Model | Cooling |  |  |  |  | Usanbolor Amartuvshin | High |  | Acc architecture finalized prerec |  | A03 - Cooling Sleeve
CO_A03_T003 | Determine Cooling Sleeve Sealing Strategy | Cooling | 2026-08-26 |  | In Progress |  | Usanbolor Amartuvshin | High |  |  |  | A03 - Cooling Sleeve
CO_A04_T001 | Acc Cooling ANSYS Model | Cooling |  |  |  |  | Theresa Franklin | High |  |  |  | A04 - Accumulator Cooling
CO_A04_T002 | Base Simulation for Acc Cooling + Feasible Configurations | Cooling | 2026-08-26 | 2026-08-30 | In Progress |  | Theresa Franklin | High |  |  |  | A04 - Accumulator Cooling
CO_A04_T003 | Preliminary Acc Cooling Testing | Cooling | 2026-08-30 | 2026-09-10 | In Progress |  | Theresa Franklin | High |  |  |  | A04 - Accumulator Cooling
FW_A01_T001 | ARG27 VD flashed on car | Firmware |  |  |  |  | Amrita Talwar |  |  |  |  | A01 - Firmware
FW_A02_T001 | SOC drawn out implementation | Firmware |  | 2026-09-28 | In Progress |  | Nathaniel Su | Medium |  |  |  | A02 - BMS Code
FW_A02_T002 | ACU bring up testing branch formed | Firmware |  | 2026-09-28 | Not Started |  | Nathaniel Su | High |  |  |  | A02 - BMS Code
FW_A02_T003 | SOC working on arg26 | Firmware |  | 2026-10-25 | Not Started |  | Nathaniel Su | High |  |  |  | A02 - BMS Code
FW_A02_T004 | LAMBMS what needs to change ready | Firmware |  | 2026-10-25 | Not Started |  | Nathaniel Su | Medium |  |  |  | A02 - BMS Code
FW_A02_T005 | Serial monitor clean up | Firmware |  | 2026-10-25 | Not Started |  | Nathaniel Su | Medium |  |  |  | A02 - BMS Code
FW_A02_T006 | SOC on arg27 | Firmware |  | 2026-11-25 | Not Started |  | Nathaniel Su | High |  |  |  | A02 - BMS Code
FW_A03_T001 | RTOS implemented on ARG26 | Firmware |  | 2026-10-25 | Not Started |  | Amrita Talwar | Medium |  |  |  | A03 - ECU Code
FW_A03_T002 | RTOS MVP | Firmware |  | 2026-09-28 | Not Started |  | Shadman Syed |  |  |  |  | A03 - ECU Code
FW_A03_T003 | RTOS testing done | Firmware |  | 2026-10-04 | Not Started |  | Shadman Syed |  |  |  |  | A03 - ECU Code
FW_A04_T001 | Lanch control simple model | Firmware |  | 2026-09-28 | Not Started |  | Xinyuan (Yolanda) Zhou | Critical |  |  |  | A04 - Active VD Controls
FW_A04_T002 | Power limiting simple model | Firmware |  | 2026-09-28 | Not Started |  | Xinyuan (Yolanda) Zhou | Critical |  |  |  | A04 - Active VD Controls
FW_A04_T003 | Regen simple model | Firmware |  | 2026-09-28 | Not Started |  | Xinyuan (Yolanda) Zhou | Critical |  |  |  | A04 - Active VD Controls
FW_A04_T004 | Torque Vectoring simple model | Firmware |  | 2026-10-25 | Not Started |  | Xinyuan (Yolanda) Zhou | Critical |  |  |  | A04 - Active VD Controls
FW_A04_T005 | Power limiting complex model | Firmware |  | 2026-11-25 | Not Started |  | Xinyuan (Yolanda) Zhou | High |  |  |  | A04 - Active VD Controls
FW_A04_T006 | Regen Complex Model | Firmware |  | 2026-11-25 | Not Started |  | Xinyuan (Yolanda) Zhou | High |  |  |  | A04 - Active VD Controls
FW_A04_T007 | Torque Vectoring Complex Model | Firmware |  | 2027-01-14 | Not Started |  | Xinyuan (Yolanda) Zhou | High |  |  | subject to change depending on JanMan | A04 - Active VD Controls
FW_A04_T008 | Launch Control Complex Modeling | Firmware |  | 2027-01-14 | Not Started |  | Xinyuan (Yolanda) Zhou | High |  |  | subject to change depending on JanMan | A04 - Active VD Controls
FW_A04_T009 | VD DTI motor Comparision | Firmware |  | 2026-09-28 | Not Started |  | Xinyuan (Yolanda) Zhou | High |  |  |  | A04 - Active VD Controls
FW_A04_T010 | VD testing plan for all four compontents | Firmware |  | 2026-09-28 | [7 empty] | A04 - Active VD Controls
FW_A04_T013 | Simplified RTOS implementation for ECU |  |  | 2026-09-15 | In Progress |  | Shadman Syed | Critical |  |  |  | A04 - Active VD Controls
FW_A04_T014 | Full RTOS port of ECU |  |  | 2026-09-26 | Blocked |  | Shadman Syed | Critical | FW_A04_T013 |  |  | A04 - Active VD Controls
FW_A04_T015 | Debug RTOS port for concurrency issues |  |  | 2026-10-03 | Not Started |  |  | High |  |  |  | A04 - Active VD Controls
FW_A04_T016 | Implementing the VD simple models | Firmware | 2026-10-05 | 2026-10-31 | Not Started |  |  | High | FW_A04_T004 |  |  | A04 - Active VD Controls
FW_A05_T001 | Diagrams done, Changes to Dash finialized | Firmware |  | 2026-09-28 | Not Started |  | Yifan Li |  |  |  |  | A05 - Dash Firmware
FW_A05_T002 | Arg26 Dash fixed | Firmware |  | 2026-10-25 | Not Started |  | Yifan Li |  |  |  |  | A05 - Dash Firmware
FW_A05_T003 | CanLib integreated to dash | Firmware |  | 2026-11-25 | Not Started |  | Yifan Li |  |  |  |  | A05 - Dash Firmware
FW_A05_T004 | dash code done | Firmware |  | 2027-01-14 | Not Started |  | Yifan Li |  |  |  |  | A05 - Dash Firmware
FW_A05_T005 | website done | Firmware |  | 2027-01-14 | Not Started |  | Yifan Li |  |  |  |  | A05 - Dash Firmware
FW_A05_T007 | Power limiting Logging off car | Firmware |  | 2026-09-28 | Not Started |  | Yifan Li |  |  |  |  | A05 - Dash Firmware
FW_A05_T006 |  | Firmware | [9 empty] | A05 - Dash Firmware
FW_A06_T001 | Telem website working | Firmware |  |  |  |  | Amrita Talwar |  |  |  |  | A06 - Other Firmware
AU_A02_T001 | Design modular ARG26 sensor mount(s) | Autonomy |  | 2026-09-09 | Not Started | AU_M001 | Teddy Duncker | Critical |  |  |  | A02 - Autonomy Mechanical
AU_A02_T002 | Calculate drag of sensor choices for Nicholas | Autonomy |  |  | Not Started |  | Teddy Duncker | Low |  |  |  | A02 - Autonomy Mechanical
AU_A02_T003 | Build steering actuator system | Autonomy |  |  | Not Started | AU_M004 | Teddy Duncker | Critical |  |  |  | A02 - Autonomy Mechanical
AU_A02_T004 | Integrate sensor mount onto ARG26 | Autonomy |  |  | Not Started | AU_M001 | Teddy Duncker | High |  |  |  | A02 - Autonomy Mechanical
AU_A02_T005 |  | Autonomy | [9 empty] | A02 - Autonomy Mechanical
AU_A03_T001 | Centerline vs. optimized analysis | Autonomy |  |  | Not Started |  | Sayee Edekar | Low |  |  | Not required | A03 - Path Planning and Following
AU_A03_T002 | Steering actuator step response transfer function generation | Autonomy |  |  | Not Started | AU_M004 | Sayee Edekar | High | AU_A02_T003 |  |  | A03 - Path Planning and Following
AU_A03_T003 | Minimum lookahead & FOV analysis | Autonomy |  | 2026-07-26 | Complete | AU_M007 | Teddy Duncker | Critical |  |  |  | A03 - Path Planning and Following
AU_A03_T004 | Model Predictive Control parameters calculated | Autonomy |  | 2026-11-01 | Not Started | AU_M004 | Sayee Edekar | Critical |  |  |  | A03 - Path Planning and Following
AU_A04_T001 | Camera choice | Autonomy |  |  | Complete | AU_M007 | Teddy Duncker | Critical |  |  |  | A04 - Sensors and Harnessing
AU_A04_T002 | LiDAR choice | Autonomy |  |  | Complete | AU_M007 | Teddy Duncker | Critical |  |  |  | A04 - Sensors and Harnessing
AU_A05_T001 | Compute module choice | Autonomy |  | 2026-08-31 | Complete | AU_M007 | Benson Zhuo | Critical |  |  |  | A05 - Compute and Hardware
AU_A05_T002 | Figure out what PCBs will be needed for safety compliance autonomy integration to ARG26 | Autonomy |  | 2026-08-28 | Complete | AU_M004 | Benson Zhuo | High |  |  |  | A05 - Compute and Hardware
AU_A05_T003 | Place order for DCU | Autonomy |  | 2026-09-18 | Not Started | AU_M004 | Benson Zhuo | Medium |  |  |  | A05 - Compute and Hardware
AU_A05_T004 | Bring up and test DCU | Autonomy |  | 2026-10-09 | Not Started | AU_M004 | Benson Zhuo | Medium | AU_A05_T003 |  |  | A05 - Compute and Hardware
AU_A05_T005 | Order RAM, storage, CAN PCIe card | Autonomy |  | 2026-09-07 | Not Started | AU_M007 | Benson Zhuo | Critical | AU_A05_T001 |  |  | A05 - Compute and Hardware
AU_A06_T001 | Buy Cones & Reflective Tape | Autonomy |  | 2026-09-07 | In Progress | AU_M001 | Emily Ng | High |  |  |  | A06 - Perception and Data Interface
AU_A06_T002 | Get Camera Data off of the Hteng Vishi to Linux/ROS | Autonomy |  | 2026-09-09 | Not Started | AU_M001 | Emily Ng | Critical |  |  |  | A06 - Perception and Data Interface
AU_A06_T003 | Determine required peripherals for putting cameras on car | Autonomy |  | 2026-09-09 | Not Started | AU_M001 | Emily Ng | Medium |  |  |  | A06 - Perception and Data Interface
AU_A06_T004 | CNN/YOLO/other detector for cone color type in autolab | Autonomy |  | 2026-09-16 | Not Started | AU_M002 | Emily Ng | High |  |  |  | A06 - Perception and Data Interface
AU_A06_T005 | Get Data off of the LiDAR | Autonomy |  | 2026-09-30 | Not Started | AU_M001 | Emily Ng | Critical |  |  | Will depend on LiDAR delivery date | A06 - Perception and Data Interface
AU_A06_T007 | Implement ground removal algorithm | Autonomy |  | 2026-10-10 | Not Started | AU_M002 | Emily Ng | High |  |  |  | A06 - Perception and Data Interface
AU_A06_T006 | Implement point clustering algorithm for LiDAR cone detection | Autonomy |  | 2026-10-15 | Not Started | AU_M002 | Emily Ng | High |  |  |  | A06 - Perception and Data Interface
AU_A07_T001 | SITL suite | Autonomy |  | 2027-01-20 | Not Started | AU_M004 | Emily Ng | Low |  |  |  | A07 - Software Pipeline
AE_A01_T001 | Aero Mounted | Aerodynamics | 2027-01-01 | 2027-03-01 | Not Started |  | Kathryn Ainley-Zoll | High |  | Aero components mounted and integrated | Milestone/completion activity | A01 - Aerodynamics
AE_A01_T002 | Manufacture Aero, Pt 1 | Aerodynamics |  |  |  |  | Kathryn Ainley-Zoll | High |  | Manufactured aerodynamic components |  | A01 - Aerodynamics
AE_A01_T003 | Finalize Aero Targets | Aerodynamics | 2026-08-01 | 2026-08-10 | In Progress |  | Kathryn Ainley-Zoll | High |  | Finalized aerodynamic targets |  | A01 - Aerodynamics
AE_A01_T004 | Post PDR Alum Outreach | Aerodynamics | 2026-09-28 | 2026-10-03 | Not Started |  | Kathryn Ainley-Zoll | Medium |  | Alumni outreach completed |  | A01 - Aerodynamics
AE_A01_T005 | Surface Modeling Training | Aerodynamics | 2026-08-24 | 2026-08-28 | Complete |  | Kathryn Ainley-Zoll | Medium |  | Completed surface modeling training |  | A01 - Aerodynamics
AE_A01_T006 | Mounting Finalized | Aerodynamics | 2026-08-01 | 2026-09-28 | Not Started |  | Kathryn Ainley-Zoll | High |  | Finalized mounting design |  | A01 - Aerodynamics
AE_A01_T007 | Mounting Manufactured | Aerodynamics | 2026-11-01 | 2026-11-30 | Not Started |  | Kathryn Ainley-Zoll | High |  | Manufactured mounting hardware |  | A01 - Aerodynamics
AE_A01_T008 | On-Car Testing | Aerodynamics | 2027-01-01 | 2027-05-01 | Not Started |  | Kathryn Ainley-Zoll | High |  | On-car aero testing results |  | A01 - Aerodynamics
AE_A01_T009 | CFD Analysis Training | Aerodynamics | 2026-08-31 | 2026-09-04 | In Progress |  | Kathryn Ainley-Zoll | High |  | Completed training |  | A01 - Aerodynamics
AE_A02_T001 | Airfoils selected for wings | Aerodynamics | 2026-09-28 | 2026-09-29 | Not Started |  | Lilly Varon | High |  | Final airfoil selection |  | A02 - Front Wing
AE_A02_T002 | Tooling for Wings and UT Made | Aerodynamics | 2026-11-01 | 2026-11-14 | Not Started |  | Lilly Varon | High |  | Wing and undertray tooling |  | A02 - Front Wing
AE_A02_T003 | Manufacturing for Wings and UT | Aerodynamics | 2027-01-01 | 2027-02-01 | Not Started |  | Lilly Varon | High |  | Manufactured wings and undertray |  | A02 - Front Wing
AE_A03_T001 | Airfoils selected for wings | Aerodynamics | 2026-09-28 | 2026-09-29 | Not Started |  | Montserrat McCoy | High |  | Final airfoil selection |  | A03 - Rear Wing
AE_A03_T002 | Tooling for Wings and UT Made | Aerodynamics | 2026-11-01 | 2026-11-14 | Not Started |  | Montserrat McCoy | High |  | Wing and undertray tooling |  | A03 - Rear Wing
AE_A03_T003 | Manufacturing for Wings and UT | Aerodynamics | 2027-01-01 | 2027-02-01 | Not Started |  | Montserrat McCoy | High |  | Manufactured wings and undertray |  | A03 - Rear Wing
AE_A04_T001 | Tooling for Wings and UT Made | Aerodynamics | 2026-11-01 | 2026-11-14 | Not Started |  | Aidan Moller | High |  | Wing and undertray tooling |  | A04 - Undertray
AE_A04_T002 | Manufacturing for Wings and UT | Aerodynamics | 2027-01-01 | 2027-02-01 | Not Started |  | Aidan Moller | High |  | Manufactured wings and undertray |  | A04 - Undertray
AE_A05_T001 | Plugs for Nosecone and Sidepods Made | Aerodynamics | 2026-10-16 | 2026-10-24 | Not Started |  | Junseok Kang | High |  | Nosecone and sidepod plugs |  | A05 - Auxiliary Elements
AE_A05_T002 | Manufacturing for Nosecone and Sidepod | Aerodynamics | 2026-10-24 | 2027-03-01 | Not Started |  | Junseok Kang | High |  | Manufactured nosecone and sidepod |  | A05 - Auxiliary Elements
AE_A06_T001 | Plugs for Nosecone and Sidepods Made | Aerodynamics | 2026-10-16 | 2026-10-24 | Not Started |  | Ethan Gu | High |  | Nosecone and sidepod plugs |  | A06 - Sidepod
AE_A06_T002 | Manufacturing for Nosecone and Sidepod | Aerodynamics | 2026-10-24 | 2027-03-01 | Not Started |  | Ethan Gu | High |  | Manufactured nosecone and sidepod |  | A06 - Sidepod
AE_A07_T001 | Choose Radiatior Location Based on CFD | Aerodynamics | 2026-08-24 | 2026-09-24 | Not Started |  | Helen Laird | High |  | Radiator location selected |  | A07 - CFD
ER_A01_T001 | Ergo mockup points identified | Ergonomics | 2026-09-07 | 2026-09-30 | Not Started |  | James King | Critical |  |  |  | A01 - Ergonomics
ER_A01_T002 | Gather Whole System Driver Load Data Points | Ergonomics | 2026-09-01 | 2026-09-12 | Not Started |  | James King | High |  |  |  | A01 - Ergonomics
ER_A01_T003 | Put Linpots on ARG26 | Ergonomics | 2026-08-31 | 2026-08-31 | Planned |  | James King | High |  |  |  | A01 - Ergonomics
ER_A01_T004 | Get Driver Max Loads | Ergonomics | 2026-08-31 | 2026-09-02 | Not Started |  | James King | High |  |  |  | A01 - Ergonomics
ER_A02_T001 | Rack and Pinion Decided | Ergonomics | 2026-09-01 | 2026-09-30 | Not Started |  | James King | High |  |  |  | A02 - Steering
ER_A02_T002 | Insert Steering column | Ergonomics | 2027-01-14 | 2027-01-16 | Not Started |  | James King | Critical |  |  |  | A02 - Steering
ER_A03_T001 | Pedal Ajustability Decided | Ergonomics | 2026-09-01 | 2026-09-12 | Not Started |  | Cameron Harvey | High |  |  |  | A03 - Pedals
ER_A03_T002 | Insert pedals | Ergonomics | 2027-01-15 | 2027-01-17 | Not Started |  | Cameron Harvey | Critical |  |  |  | A03 - Pedals
ER_A03_T003 | Determine Lockup force | Ergonomics |  |  |  |  | Cameron Harvey |  |  |  |  | A03 - Pedals
ER_A03_T004 | Order Tilton Prodcuts for pedals | Ergonomics |  |  |  |  | Cameron Harvey |  |  |  |  | A03 - Pedals
ER_A04_T001 | Drivers Molds Taken | Ergonomics | 2026-10-18 | 2026-10-24 | Not Started |  | James King | High |  |  |  | A04 - Seat
ER_A04_T002 | Driver Seat Scans in CAD | Ergonomics | 2026-10-25 | 2026-10-31 | Not Started |  | James King | High |  |  |  | A04 - Seat
ER_A04_T003 | Seat Upper Constraint Solution | Ergonomics | 2026-09-01 | 2026-09-30 | Not Started |  | James King | High |  |  |  | A04 - Seat
ER_A04_T004 | Make Plug for New Seat | Ergonomics | 2026-11-16 | 2026-11-27 | Not Started |  | James King | High |  |  |  | A04 - Seat
ER_A04_T005 | Layup New Driver Seat | Ergonomics | 2026-11-30 | 2026-12-11 | Not Started |  | James King | High |  |  |  | A04 - Seat
ER_A05_T001 | Order Firewall/Backups | Ergonomics | 2026-12-11 | 2026-12-16 | Not Started |  | James King | High |  |  |  | A05 - Firewall
ER_A05_T002 | Mount Firewall | Ergonomics | 2027-01-18 | 2027-01-18 | Not Started |  | James King | Critical |  |  |  | A05 - Firewall
ER_A06_T001 | Mount Head Restraint | Ergonomics | 2027-01-17 | 2027-01-18 | Not Started |  | James King | Critical |  |  |  | A06 - Head Restraint
ER_A06_T002 | Decide on mounting method of Head Restraint | Ergonomics | 2026-09-07 | 2026-09-30 | Not Started |  | James King | High |  |  |  | A06 - Head Restraint
MO_A01_T001 | Ordering Composite Materials | Monocoque | 2026-07-27 | 2026-08-14 | In Progress |  | Katherine Collard | Low |  |  |  | A01 - Monocoque
MO_A01_T002 |  | Monocoque |  |  | Not Started |  | Katherine Collard | Critical |  |  |  | A01 - Monocoque
MO_A01_T003 | Select foam and plug manufacturing process | Monocoque | 2026-08-30 | 2026-08-31 | Not Started |  | Katherine Collard | Critical |  | Documented foam/plug process and manufacturing location | Decide in-house vs. Woodward and old vs. new plugs. | A01 - Monocoque
MO_A01_T004 | Trial mold gel coat process | Monocoque | 2026-09-03 | 2026-09-03 | Not Started |  | Katherine Collard | Medium |  | Gel coat trial results |  | A01 - Monocoque
MO_A01_T005 | Pre-process plug with Dolphin Glaze or selected filler | Monocoque | 2026-09-07 | 2026-09-14 | Not Started |  | Katherine Collard | High |  | Prepared plug surface |  | A01 - Monocoque
MO_A01_T006 | Receive carbon materials | Monocoque | 2026-09-07 | 2026-09-07 | Not Started |  | Katherine Collard | Critical |  | Carbon available for layups |  | A01 - Monocoque
MO_A01_T007 | Print drilling and assembly jigs | Monocoque | 2026-10-22 | 2026-11-01 | Not Started |  | Katherine Collard | High |  | Printed jigs |  | A01 - Monocoque
MO_A01_T008 | Cut Delrin jig rods | Monocoque | 2026-10-23 | 2026-11-01 | Not Started |  | Katherine Collard | High |  | Cut Delrin rods |  | A01 - Monocoque
MO_A01_T009 | Source all jigging materials for monocoque holes | Monocoque | 2026-10-16 | 2026-10-24 | Not Started |  | Katherine Collard | Critical |  | Complete jigging material kit |  | A01 - Monocoque
MO_A01_T010 | Order drill-bushing stock | Monocoque | 2026-10-25 | 2026-10-25 | Not Started |  | Katherine Collard | High |  | Drill-bushing stock ordered |  | A01 - Monocoque
MO_A01_T011 | Drill monocoque holes using jigs | Monocoque | 2026-11-01 | 2026-11-03 | Not Started |  | Katherine Collard | Critical |  | Monocoque holes drilled to jig | Assumes continuous labor support. | A01 - Monocoque
MO_A01_T012 | Finish new-plug-to-post-process sequence | Monocoque | 2026-10-19 | 2026-11-04 | Not Started |  | Katherine Collard | Critical |  | Post-processed plug | Calendar indicates a 16-day duration. | A01 - Monocoque
MO_A01_T013 | Manufacture all drill bushings | Monocoque | 2026-11-06 | 2026-11-06 | Not Started |  | Katherine Collard | Critical |  | Completed drill bushings |  | A01 - Monocoque
MO_A01_T014 | Prepare all materials for mold manufacturing | Monocoque | 2026-11-07 | 2026-11-07 | Not Started |  | Katherine Collard | Critical |  | Mold manufacturing material kit |  | A01 - Monocoque
MO_A01_T015 | Complete puck development | Monocoque | 2026-11-08 | 2026-11-08 | Not Started |  | Katherine Collard | High |  | Puck design/manufacturing progress | Calendar note is tentative. | A01 - Monocoque
MO_A01_T016 | Finish plug preparation | Monocoque | 2026-11-11 | 2026-11-11 | Not Started |  | Katherine Collard | Critical |  | Plug ready for mold manufacture |  | A01 - Monocoque
MO_A01_T017 | Attempt wet-layup mold if ahead of schedule | Monocoque | 2026-11-14 | 2026-11-15 | Not Started |  | Katherine Collard | Low |  | Optional wet-layup mold trial | Stretch task; potentially both molds. | A01 - Monocoque
MO_A01_T018 | Release first mold | Monocoque | 2026-11-19 | 2026-11-19 | Not Started |  | Katherine Collard | High |  | First mold released |  | A01 - Monocoque
MO_A01_T019 | Prepare everything required for mold layup | Monocoque | 2026-11-30 | 2026-11-30 | Not Started |  | Katherine Collard | Critical |  | Mold layup readiness sign-off |  | A01 - Monocoque
MO_A01_T020 | Post-process molds | Monocoque | 2026-12-02 | 2026-12-02 | Not Started |  | Katherine Collard | High |  | Post-processed molds |  | A01 - Monocoque
MO_A01_T021 | Prepare molds, oven, carbon kits, and tooling for JanMan | Monocoque | 2027-01-04 | 2027-01-06 | Not Started |  | Katherine Collard | Critical |  | JanMan manufacturing readiness |  | A01 - Monocoque
MO_A01_T022 | Lay up first monocoque skin | Monocoque | 2027-01-07 | 2027-01-09 | Not Started |  | Katherine Collard | Critical |  | First skin laid up |  | A01 - Monocoque
MO_A01_T023 | Complete first cure and oven cycle | Monocoque | 2027-01-10 | 2027-01-10 | Not Started |  | Katherine Collard | Critical |  | First skin cured |  | A01 - Monocoque
MO_A01_T024 | Install and bond core | Monocoque | 2027-01-11 | 2027-01-13 | Not Started |  | Katherine Collard | Critical |  | Core installed | SES due date uncertainty noted on Jan. 12. | A01 - Monocoque
MO_A01_T025 | Lay up second monocoque skin | Monocoque | 2027-01-14 | 2027-01-16 | Not Started |  | Katherine Collard | Critical |  | Second skin laid up |  | A01 - Monocoque
MO_A01_T026 | Complete final cure | Monocoque | 2027-01-17 | 2027-01-17 | Not Started |  | Katherine Collard | Critical |  | Monocoque fully cured |  | A01 - Monocoque
MO_A01_T027 | Support powertrain integration | Monocoque | 2027-02-07 | 2027-02-07 | Not Started |  | Katherine Collard | High |  | Powertrain integration support complete |  | A01 - Monocoque
MO_A01_T028 | ANSYS 3 point bend test model | Monocoque | 2026-07-27 | 2026-08-07 | Not Started |  | Katherine Collard | Medium |  | model that can be easily tested for new data |  | A01 - Monocoque
MO_A01_T029 | ANSYS Twist Test | Monocoque | 2026-07-27 | 2026-08-24 | Not Started |  | Katherine Collard | Medium |  |  |  | A01 - Monocoque
MO_A01_T030 |  | Monocoque |  |  | Not Started |  | Katherine Collard | Critical |  | Validated ANSYS 3-point bend model/test plan | Calendar note asks whether testing is complete. | A01 - Monocoque
MO_A01_T031 |  | Monocoque |  |  | Not Started |  | Katherine Collard | Critical |  | Completed 3-point bend simulation set |  | A01 - Monocoque
MO_A02_T001 | Finalize monocoque CAD with points | Monocoque | 2026-09-01 | 2026-10-19 | Not Started |  | Katherine Collard | Medium |  | Updated monocoque CAD |  | A02 - MO Geometry
MO_A02_T002 | Update new monocoque CAD geometry | Monocoque | 2026-08-24 | 2026-09-30 | In Progress |  | Katherine Collard | Medium |  | Updated CAD geometry | No-redesign schedule assumes geometry changes remain limited. | A02 - MO Geometry
MO_A02_T003 | Lock monocoque CAD points | Monocoque | 2026-10-19 | 2026-10-19 | Not Started |  | Katherine Collard | Critical |  | Locked monocoque reference points |  | A02 - MO Geometry
MO_A05_T001 | Ply Schedule Testing | Monocoque | [9 empty] | A05 - SES and Ply Schedules
MO_A05_T002 | Consult professional about laminates | Monocoque | 2026-08-11 | 2026-08-31 | Not Started |  |  | High |  | Material testing guidance and action items |  | A05 - SES and Ply Schedules
MO_A05_T003 | Run ANSYS twist-test ply schedule study | Monocoque | 2026-08-13 | 2026-09-11 | Not Started |  |  | Low |  | Twist-test ply schedule results |  | A05 - SES and Ply Schedules
MO_A05_T004 | Analyze panel test results | Monocoque | 2026-09-19 | 2026-09-19 | Not Started |  |  | Critical |  | Analyzed panel results and recommendations |  | A05 - SES and Ply Schedules
MO_A05_T005 | Complete additional test-panel round | Monocoque | 2026-09-27 | 2026-10-04 | Not Started |  |  | High |  | Additional panel test results | Calendar notes another panel round; one-week window assumed. | A05 - SES and Ply Schedules
MO_A05_T006 | Complete SES work session | Monocoque | 2026-11-05 | 2026-11-05 | Not Started |  |  | Critical |  | Updated SES package |  | A05 - SES and Ply Schedules
MO_A05_T007 | Continue test panels and SES documentation | Monocoque | 2026-11-09 | 2026-11-10 | Not Started |  |  | Critical |  | Updated SES test evidence |  | A05 - SES and Ply Schedules
MO_A05_T008 | Lock final ply schedules | Monocoque | 2026-09-30 | 2026-11-20 | Not Started |  |  | Critical |  | Released ply schedule |  | A05 - SES and Ply Schedules
MO_A05_T009 | Submit SES package | Monocoque | 2026-12-01 | 2026-12-01 | Not Started |  |  | Critical |  | Submitted SES package |  | A05 - SES and Ply Schedules
MO_A05_T010 | Test Panel Jigs and Elastic Modulus | Monocoque | 2026-08-17 | 2026-08-21 | Not Started |  |  | High |  | 1. Have 3 pt bending jig 2. Have an elastic modulus tested thats rules compliant 3. test T1100 4. Other testing jigs (1-2 must be done) |  | A05 - SES and Ply Schedules
SU_A01_T001 | Run ARG26 CG Test | Suspension | 2026-08-31 | 2026-09-05 | Not Started |  | Davis Rattanavijai |  |  |  | Very very valuable information | A01 - Suspension
SU_A01_T002 | GRIND KINEMATIC POINTS | Suspension | 2026-09-06 | 2026-09-13 | Not Started |  | Davis Rattanavijai |  | SU_A01_T003 |  |  | A01 - Suspension
SU_A01_T003 | Gather Design Necessary Car Data | Suspension | 2026-09-05 | 2026-09-19 | Not Started |  | Davis Rattanavijai |  |  |  | Max lateral, longitudinal acceleration and more to come | A01 - Suspension
SU_A01_T004 | test task | Suspension | [9 empty] | A01 - Suspension
SU_A02_T001 | Links manufacturing | Suspension | 2026-11-01 | 2027-01-15 | Not Started |  | Daniel Wtorkowski |  |  |  |  | A02 - Links
SU_A02_T002 | Calculate Link Dimensions (Length, OD and Wall thickness) | Suspension |  |  | Not Started |  | Daniel Wtorkowski | High |  |  |  | A02 - Links
SU_A02_T003 | First Round CAD of links and adapters | Suspension |  |  | Not Started |  | Daniel Wtorkowski | Medium | SU_A01_T002 |  |  | A02 - Links
SU_A02_T004 | Optimize Upper Adapter Geometry | Suspension |  |  | Not Started |  | Daniel Wtorkowski | Medium | SU_A02_T003 |  |  | A02 - Links
SU_A02_T005 | Order rod ends, bearings, tube stock from McMaster | Suspension |  |  | Not Started |  | Daniel Wtorkowski | Medium |  |  |  | A02 - Links
SU_A02_T006 | Order adapters from ZTL | Suspension |  |  | Not Started |  | Daniel Wtorkowski | High |  |  |  | A02 - Links
SU_A02_T007 | Machine Inserts | Suspension |  |  | Not Started |  | Daniel Wtorkowski | High |  |  |  | A02 - Links
SU_A02_T008 | Manufacture push links for strain gauge installation as well as spares | Suspension |  |  | Not Started |  | Daniel Wtorkowski | High |  |  |  | A02 - Links
SU_A03_T001 | Clevises manufacturing | Suspension | 2026-11-01 | 2027-01-15 | Not Started | [6 empty] | A03 - Clevises
SU_A03_T002 | Devcon Clevises | Suspension | 2027-01-21 | 2027-01-22 | Not Started | [6 empty] | A03 - Clevises
SU_A04_T001 | Rockers outsourced | Suspension | 2026-11-01 | 2027-01-15 | Not Started |  | Aarian Mepani |  |  |  |  | A04 - Rockers
SU_A05_T001 | Lock down ARB architecture | Suspension |  | 2026-09-21 | Not Started |  | Alice Jones | High |  | Decide on ARB front and rear architecture |  | A05 - Anti-Roll
SU_A05_T002 | First ARB CAD pass | Suspension |  | 2026-09-28 | Not Started |  | Alice Jones | Medium |  | Have an initial CAD assembly ready for PDR |  | A05 - Anti-Roll
SU_A05_T003 | Refine torsion bar sizing, Optimise blade geometry, Validate stiffness targets | Suspension | 2026-09-28 | 2026-10-24 | Not Started |  | Alice Jones | Medium |  |  |  | A05 - Anti-Roll
SU_A05_T004 | Design ARB Mounts and Adapters | Suspension | 2026-10-10 | 2026-10-24 | Not Started |  | Alice Jones | Medium |  |  |  | A05 - Anti-Roll
SU_A05_T005 | ARB CAD Freeze | Suspension | 2026-10-24 | 2026-11-05 | Not Started |  | Alice Jones | Medium |  |  | Straight After FDR | A05 - Anti-Roll
SU_A05_T006 | Place orders for outsourced ARB components | Suspension | 2026-11-05 | 2026-11-08 | Not Started |  | Alice Jones | Medium |  |  |  | A05 - Anti-Roll
SU_A05_T007 | Manufacture 50% of in-house ARB components | Suspension | 2026-11-08 | 2026-12-13 | Not Started |  | Alice Jones | Medium |  |  |  | A05 - Anti-Roll
SU_A05_T008 | Complete remaining ARB machining | Suspension | 2027-01-01 | 2027-01-15 | Not Started |  | Alice Jones | Medium |  |  |  | A05 - Anti-Roll
SU_A05_T009 | Assemble complete ARB | Suspension | 2027-01-15 | 2027-01-18 | Not Started |  | Alice Jones | Medium |  |  |  | A05 - Anti-Roll
SU_A05_T010 | Integrate ARB onto chassis with other suspension components | Suspension | 2027-01-18 | 2027-01-24 | Not Started |  | Alice Jones | Medium |  |  |  | A05 - Anti-Roll
BU_A01_T001 | Professonally Wrap Car | Business | 2027-02-12 | 2027-02-15 | Not Started |  |  | High |  |  |  | A01 - Business
BU_A01_T003 | Finalize Comp Documents | Business | 2027-05-01 | 2027-05-05 | [7 empty] | A01 - Business
BU_A02_T001 | Publish Purchasing sheet | Business | 2026-08-28 | 2026-08-30 | In Progress |  |  | High |  |  |  | A02 - Purchasing
BU_A03_T001 | Upperclassmen Delibs 1 | Business | 2026-09-08 | 2026-09-08 | Not Started | [6 empty] | A03 - Recruitment
BU_A03_T002 | Upperclassmen interviews | Business | 2026-09-06 | 2026-09-14 | [7 empty] | A03 - Recruitment
BU_A03_T003 | Project Team Fest | Business |  | 2026-09-01 | Complete | [6 empty] | A03 - Recruitment
BU_A03_T004 | Info Session 1 | Business |  | 2026-09-02 | Complete | [6 empty] | A03 - Recruitment
BU_A03_T005 | Info Session 2 | Business |  | 2026-09-15 | [7 empty] | A03 - Recruitment
BU_A03_T006 | Info Session 3 | Business |  | 2026-09-21 | [7 empty] | A03 - Recruitment
BU_A03_T007 | Info Session 4 | Business |  | 2026-10-07 | [7 empty] | A03 - Recruitment
BU_A03_T008 | First Year Delibs 1 | Business | 2026-10-17 | 2026-10-18 | [7 empty] | A03 - Recruitment
BU_A03_T009 | Upperclassmen Final Delibs | Business | 2026-10-12 | 2026-10-13 | [7 empty] | A03 - Recruitment
BU_A03_T010 | First Year Interviews | Business | 2026-10-20 | 2026-10-27 | [7 empty] | A03 - Recruitment
BU_A03_T011 | First Year Final Delibs | Business | 2026-10-31 | 2026-11-01 | [7 empty] | A03 - Recruitment
BU_A06_T001 | Finalize website | Business | 2026-08-24 | 2026-08-27 | Complete |  | Sayee Edekar | Low |  |  |  | A06 - Website

## Timeline Driver (hidden)
ID | Task | Subteam | Start | Due | Status
GE_A00_T001 | Subteam part designer sprints | General | 2026-08-31 | 2026-09-04 | In Progress
GE_A00_T002 | Tuning for Toronto Shootout | General | 2026-09-21 | 2026-09-30 | Not Started
GE_A00_T003 | Pack for Toronto Shootout | General | 2026-10-01 | 2026-10-02 | Not Started
GE_A00_T004 | Tech inspection for Toronto Shootout | General | 2026-09-28 | 2026-09-30 | Not Started
GE_A01_T001 | Mech Check outs for ARG26 | Chassis | 2026-08-30 | 2026-09-01 | Complete
GE_A01_T002 | ARG26 Bolt Check | Chassis | 2026-08-30 | 2026-08-31 | In Progress
GE_A02_T001 | EV Check outs for ARG26 | Powertrain | 2026-08-31 | 2026-09-02 | Not Started
GE_A02_T002 | Sensor integration on ARG26 | Powertrain | 2026-09-01 | 2026-09-05 | Not Started
GE_A02_T003 | Charging ARG26 pack | Powertrain | 2026-09-02 | 2026-09-04 | Complete
HV_A01_T001 | test task | High Voltage
LV_A01_T001 | Altium library basics finished | Low Voltage | 2026-07-13 | 2026-08-09 | Review
LV_A04_T001 | Design first rev of BMS Child | Low Voltage | 2026-08-01 | 2026-09-01 | In Progress
LV_A04_T002 | Test/debug first rev of BMS child | Low Voltage | 2026-09-07 | 2026-09-21 | Not Started
LV_A04_T003 | Validate communication between BMS child/mother | Low Voltage | 2026-09-21 | 2026-10-01 | Not Started
LV_A04_T004 | Design final rev of BMS child for module integration | Low Voltage | 2026-10-01 | 2026-11-16 | Not Started
LV_A04_T005 | Test final rev of BMS child | Low Voltage | 2026-11-23 | 2026-12-01 | Not Started
LV_A04_T006 | Bring up + validate all BMS children + spares | Low Voltage | 2026-12-01 | 2027-01-15 | Not Started
LV_A06_T001 | Shutdown circuit closes | Low Voltage |  |  | Not Started
LV_A07_T001 | Precharge and discharge validated | Low Voltage |  |  | Not Started
LV_A08_T001 | Get PDM08 and ACC3s | Low Voltage | 2026-08-09 | 2026-09-07 | Not Started
LV_A08_T002 | HV DCDC/LV DCDC Choice | Low Voltage |  |  | In Progress
LV_A08_T003 | Design first rev of PDU | Low Voltage | 2026-08-05 | 2026-09-05 | Not Started
LV_A09_T001 | Dash multple screens | Low Voltage |  |  | Not Started
LV_A09_T002 | Design first rev of Dash | Low Voltage |  |  | Planned
LV_A09_T003 | Order Dash components | Low Voltage |  |  | Not Started
LV_A09_T004 | Bring up + Test Dash rev1 | Low Voltage |  |  | Not Started
LV_A09_T005 | Dash harnessing | Low Voltage |  |  | Not Started
LV_A09_T006 | Dash integration | Low Voltage |  |  | Not Started
LV_A09_T007 | Bring up final rev Dash spares | Low Voltage |  |  | Not Started
CO_A02_T002 | Run full liquid loop pressure drop test | Cooling |  |  | Not Started
CO_A02_T009 | Identify system parameters w/ hand calcs and data |  |  |  | Not Started
CO_A02_T003 | Determine necessary radiator and fan specifications | Cooling | 2026-09-08 | 2026-09-11 | Not Started
CO_A02_T004 | Order stock radiator for testing | Cooling | 2026-09-15 | 2026-09-20 | Not Started
CO_A02_T005 | Test and confirm geometry/layout | Cooling | 2026-09-15 | 2026-09-25 | Not Started
CO_A02_T001 | PRIORITY: order custom radiator | Cooling | 2026-09-11 | 2026-09-30 | Not Started
CO_A02_T006 | Manufacture liquid loop prototype | Cooling | 2026-10-01 | 2026-10-08 | Not Started
CO_A02_T007 | Conduct tests and collect data for pressure drop and heat rejection | Cooling | 2026-10-10 | 2026-10-17 | Not Started
CO_A02_T008 | Assemble final liquid loop on bench | Cooling | 2027-01-04 | 2027-01-15 | Not Started
CO_A02_T010 | Calibrate Temp sensors and put on car for endurance testing | Cooling | 2026-09-04 | 2026-09-04 | Not Started
CO_A03_T001 | Run motor sleeve heat rejection + flow test | Cooling
CO_A03_T002 | Cooling Sleeve ANSYS Model | Cooling
CO_A03_T003 | Determine Cooling Sleeve Sealing Strategy | Cooling | 2026-08-26 |  | In Progress
CO_A04_T001 | Acc Cooling ANSYS Model | Cooling
CO_A04_T002 | Base Simulation for Acc Cooling + Feasible Configurations | Cooling | 2026-08-26 | 2026-08-30 | In Progress
CO_A04_T003 | Preliminary Acc Cooling Testing | Cooling | 2026-08-30 | 2026-09-10 | In Progress
FW_A01_T001 | ARG27 VD flashed on car | Firmware
FW_A02_T001 | SOC drawn out implementation | Firmware |  | 2026-09-28 | In Progress
FW_A02_T002 | ACU bring up testing branch formed | Firmware |  | 2026-09-28 | Not Started
FW_A02_T003 | SOC working on arg26 | Firmware |  | 2026-10-25 | Not Started
FW_A02_T004 | LAMBMS what needs to change ready | Firmware |  | 2026-10-25 | Not Started
FW_A02_T005 | Serial monitor clean up | Firmware |  | 2026-10-25 | Not Started
FW_A02_T006 | SOC on arg27 | Firmware |  | 2026-11-25 | Not Started
FW_A03_T001 | RTOS implemented on ARG26 | Firmware |  | 2026-10-25 | Not Started
FW_A03_T002 | RTOS MVP | Firmware |  | 2026-09-28 | Not Started
FW_A03_T003 | RTOS testing done | Firmware |  | 2026-10-04 | Not Started
FW_A04_T001 | Lanch control simple model | Firmware |  | 2026-09-28 | Not Started
FW_A04_T002 | Power limiting simple model | Firmware |  | 2026-09-28 | Not Started
FW_A04_T003 | Regen simple model | Firmware |  | 2026-09-28 | Not Started
FW_A04_T004 | Torque Vectoring simple model | Firmware |  | 2026-10-25 | Not Started
FW_A04_T005 | Power limiting complex model | Firmware |  | 2026-11-25 | Not Started
FW_A04_T006 | Regen Complex Model | Firmware |  | 2026-11-25 | Not Started
FW_A04_T007 | Torque Vectoring Complex Model | Firmware |  | 2027-01-14 | Not Started
FW_A04_T008 | Launch Control Complex Modeling | Firmware |  | 2027-01-14 | Not Started
FW_A04_T009 | VD DTI motor Comparision | Firmware |  | 2026-09-28 | Not Started
FW_A04_T010 | VD testing plan for all four compontents | Firmware |  | 2026-09-28
FW_A04_T013 | Simplified RTOS implementation for ECU |  |  | 2026-09-15 | In Progress
FW_A04_T014 | Full RTOS port of ECU |  |  | 2026-09-26 | Blocked
FW_A04_T015 | Debug RTOS port for concurrency issues |  |  | 2026-10-03 | Not Started
FW_A04_T016 | Implementing the VD simple models | Firmware | 2026-10-05 | 2026-10-31 | Not Started
FW_A05_T001 | Diagrams done, Changes to Dash finialized | Firmware |  | 2026-09-28 | Not Started
FW_A05_T002 | Arg26 Dash fixed | Firmware |  | 2026-10-25 | Not Started
FW_A05_T003 | CanLib integreated to dash | Firmware |  | 2026-11-25 | Not Started
FW_A05_T004 | dash code done | Firmware |  | 2027-01-14 | Not Started
FW_A05_T005 | website done | Firmware |  | 2027-01-14 | Not Started
FW_A05_T007 | Power limiting Logging off car | Firmware |  | 2026-09-28 | Not Started
FW_A05_T006 |  | Firmware
FW_A06_T001 | Telem website working | Firmware
AU_A02_T001 | Design modular ARG26 sensor mount(s) | Autonomy |  | 2026-09-09 | Not Started
AU_A02_T002 | Calculate drag of sensor choices for Nicholas | Autonomy |  |  | Not Started
AU_A02_T003 | Build steering actuator system | Autonomy |  |  | Not Started
AU_A02_T004 | Integrate sensor mount onto ARG26 | Autonomy |  |  | Not Started
AU_A02_T005 |  | Autonomy
AU_A03_T001 | Centerline vs. optimized analysis | Autonomy |  |  | Not Started
AU_A03_T002 | Steering actuator step response transfer function generation | Autonomy |  |  | Not Started
AU_A03_T003 | Minimum lookahead & FOV analysis | Autonomy |  | 2026-07-26 | Complete
AU_A03_T004 | Model Predictive Control parameters calculated | Autonomy |  | 2026-11-01 | Not Started
AU_A04_T001 | Camera choice | Autonomy |  |  | Complete
AU_A04_T002 | LiDAR choice | Autonomy |  |  | Complete
AU_A05_T001 | Compute module choice | Autonomy |  | 2026-08-31 | Complete
AU_A05_T002 | Figure out what PCBs will be needed for safety compliance autonomy integration to ARG26 | Autonomy |  | 2026-08-28 | Complete
AU_A05_T003 | Place order for DCU | Autonomy |  | 2026-09-18 | Not Started
AU_A05_T004 | Bring up and test DCU | Autonomy |  | 2026-10-09 | Not Started
AU_A05_T005 | Order RAM, storage, CAN PCIe card | Autonomy |  | 2026-09-07 | Not Started
AU_A06_T001 | Buy Cones & Reflective Tape | Autonomy |  | 2026-09-07 | In Progress
AU_A06_T002 | Get Camera Data off of the Hteng Vishi to Linux/ROS | Autonomy |  | 2026-09-09 | Not Started
AU_A06_T003 | Determine required peripherals for putting cameras on car | Autonomy |  | 2026-09-09 | Not Started
AU_A06_T004 | CNN/YOLO/other detector for cone color type in autolab | Autonomy |  | 2026-09-16 | Not Started
AU_A06_T005 | Get Data off of the LiDAR | Autonomy |  | 2026-09-30 | Not Started
AU_A06_T007 | Implement ground removal algorithm | Autonomy |  | 2026-10-10 | Not Started
AU_A06_T006 | Implement point clustering algorithm for LiDAR cone detection | Autonomy |  | 2026-10-15 | Not Started
AU_A07_T001 | SITL suite | Autonomy |  | 2027-01-20 | Not Started
AE_A01_T001 | Aero Mounted | Aerodynamics | 2027-01-01 | 2027-03-01 | Not Started
AE_A01_T002 | Manufacture Aero, Pt 1 | Aerodynamics
AE_A01_T003 | Finalize Aero Targets | Aerodynamics | 2026-08-01 | 2026-08-10 | In Progress
AE_A01_T004 | Post PDR Alum Outreach | Aerodynamics | 2026-09-28 | 2026-10-03 | Not Started
AE_A01_T005 | Surface Modeling Training | Aerodynamics | 2026-08-24 | 2026-08-28 | Complete
AE_A01_T006 | Mounting Finalized | Aerodynamics | 2026-08-01 | 2026-09-28 | Not Started
AE_A01_T007 | Mounting Manufactured | Aerodynamics | 2026-11-01 | 2026-11-30 | Not Started
AE_A01_T008 | On-Car Testing | Aerodynamics | 2027-01-01 | 2027-05-01 | Not Started
AE_A01_T009 | CFD Analysis Training | Aerodynamics | 2026-08-31 | 2026-09-04 | In Progress
AE_A02_T001 | Airfoils selected for wings | Aerodynamics | 2026-09-28 | 2026-09-29 | Not Started
AE_A02_T002 | Tooling for Wings and UT Made | Aerodynamics | 2026-11-01 | 2026-11-14 | Not Started
AE_A02_T003 | Manufacturing for Wings and UT | Aerodynamics | 2027-01-01 | 2027-02-01 | Not Started
AE_A03_T001 | Airfoils selected for wings | Aerodynamics | 2026-09-28 | 2026-09-29 | Not Started
AE_A03_T002 | Tooling for Wings and UT Made | Aerodynamics | 2026-11-01 | 2026-11-14 | Not Started
AE_A03_T003 | Manufacturing for Wings and UT | Aerodynamics | 2027-01-01 | 2027-02-01 | Not Started
AE_A04_T001 | Tooling for Wings and UT Made | Aerodynamics | 2026-11-01 | 2026-11-14 | Not Started
AE_A04_T002 | Manufacturing for Wings and UT | Aerodynamics | 2027-01-01 | 2027-02-01 | Not Started
AE_A05_T001 | Plugs for Nosecone and Sidepods Made | Aerodynamics | 2026-10-16 | 2026-10-24 | Not Started
AE_A05_T002 | Manufacturing for Nosecone and Sidepod | Aerodynamics | 2026-10-24 | 2027-03-01 | Not Started
AE_A06_T001 | Plugs for Nosecone and Sidepods Made | Aerodynamics | 2026-10-16 | 2026-10-24 | Not Started
AE_A06_T002 | Manufacturing for Nosecone and Sidepod | Aerodynamics | 2026-10-24 | 2027-03-01 | Not Started
AE_A07_T001 | Choose Radiatior Location Based on CFD | Aerodynamics | 2026-08-24 | 2026-09-24 | Not Started
ER_A01_T001 | Ergo mockup points identified | Ergonomics | 2026-09-07 | 2026-09-30 | Not Started
ER_A01_T002 | Gather Whole System Driver Load Data Points | Ergonomics | 2026-09-01 | 2026-09-12 | Not Started
ER_A01_T003 | Put Linpots on ARG26 | Ergonomics | 2026-08-31 | 2026-08-31 | Planned
ER_A01_T004 | Get Driver Max Loads | Ergonomics | 2026-08-31 | 2026-09-02 | Not Started
ER_A02_T001 | Rack and Pinion Decided | Ergonomics | 2026-09-01 | 2026-09-30 | Not Started
ER_A02_T002 | Insert Steering column | Ergonomics | 2027-01-14 | 2027-01-16 | Not Started
ER_A03_T001 | Pedal Ajustability Decided | Ergonomics | 2026-09-01 | 2026-09-12 | Not Started
ER_A03_T002 | Insert pedals | Ergonomics | 2027-01-15 | 2027-01-17 | Not Started
ER_A03_T003 | Determine Lockup force | Ergonomics
ER_A03_T004 | Order Tilton Prodcuts for pedals | Ergonomics
ER_A04_T001 | Drivers Molds Taken | Ergonomics | 2026-10-18 | 2026-10-24 | Not Started
ER_A04_T002 | Driver Seat Scans in CAD | Ergonomics | 2026-10-25 | 2026-10-31 | Not Started
ER_A04_T003 | Seat Upper Constraint Solution | Ergonomics | 2026-09-01 | 2026-09-30 | Not Started
ER_A04_T004 | Make Plug for New Seat | Ergonomics | 2026-11-16 | 2026-11-27 | Not Started
ER_A04_T005 | Layup New Driver Seat | Ergonomics | 2026-11-30 | 2026-12-11 | Not Started
ER_A05_T001 | Order Firewall/Backups | Ergonomics | 2026-12-11 | 2026-12-16 | Not Started
ER_A05_T002 | Mount Firewall | Ergonomics | 2027-01-18 | 2027-01-18 | Not Started
ER_A06_T001 | Mount Head Restraint | Ergonomics | 2027-01-17 | 2027-01-18 | Not Started
ER_A06_T002 | Decide on mounting method of Head Restraint | Ergonomics | 2026-09-07 | 2026-09-30 | Not Started
MO_A01_T001 | Ordering Composite Materials | Monocoque | 2026-07-27 | 2026-08-14 | In Progress
MO_A01_T002 |  | Monocoque |  |  | Not Started
MO_A01_T003 | Select foam and plug manufacturing process | Monocoque | 2026-08-30 | 2026-08-31 | Not Started
MO_A01_T004 | Trial mold gel coat process | Monocoque | 2026-09-03 | 2026-09-03 | Not Started
MO_A01_T005 | Pre-process plug with Dolphin Glaze or selected filler | Monocoque | 2026-09-07 | 2026-09-14 | Not Started
MO_A01_T006 | Receive carbon materials | Monocoque | 2026-09-07 | 2026-09-07 | Not Started
MO_A01_T007 | Print drilling and assembly jigs | Monocoque | 2026-10-22 | 2026-11-01 | Not Started
MO_A01_T008 | Cut Delrin jig rods | Monocoque | 2026-10-23 | 2026-11-01 | Not Started
MO_A01_T009 | Source all jigging materials for monocoque holes | Monocoque | 2026-10-16 | 2026-10-24 | Not Started
MO_A01_T010 | Order drill-bushing stock | Monocoque | 2026-10-25 | 2026-10-25 | Not Started
MO_A01_T011 | Drill monocoque holes using jigs | Monocoque | 2026-11-01 | 2026-11-03 | Not Started
MO_A01_T012 | Finish new-plug-to-post-process sequence | Monocoque | 2026-10-19 | 2026-11-04 | Not Started
MO_A01_T013 | Manufacture all drill bushings | Monocoque | 2026-11-06 | 2026-11-06 | Not Started
MO_A01_T014 | Prepare all materials for mold manufacturing | Monocoque | 2026-11-07 | 2026-11-07 | Not Started
MO_A01_T015 | Complete puck development | Monocoque | 2026-11-08 | 2026-11-08 | Not Started
MO_A01_T016 | Finish plug preparation | Monocoque | 2026-11-11 | 2026-11-11 | Not Started
MO_A01_T017 | Attempt wet-layup mold if ahead of schedule | Monocoque | 2026-11-14 | 2026-11-15 | Not Started
MO_A01_T018 | Release first mold | Monocoque | 2026-11-19 | 2026-11-19 | Not Started
MO_A01_T019 | Prepare everything required for mold layup | Monocoque | 2026-11-30 | 2026-11-30 | Not Started
MO_A01_T020 | Post-process molds | Monocoque | 2026-12-02 | 2026-12-02 | Not Started
MO_A01_T021 | Prepare molds, oven, carbon kits, and tooling for JanMan | Monocoque | 2027-01-04 | 2027-01-06 | Not Started
MO_A01_T022 | Lay up first monocoque skin | Monocoque | 2027-01-07 | 2027-01-09 | Not Started
MO_A01_T023 | Complete first cure and oven cycle | Monocoque | 2027-01-10 | 2027-01-10 | Not Started
MO_A01_T024 | Install and bond core | Monocoque | 2027-01-11 | 2027-01-13 | Not Started
MO_A01_T025 | Lay up second monocoque skin | Monocoque | 2027-01-14 | 2027-01-16 | Not Started
MO_A01_T026 | Complete final cure | Monocoque | 2027-01-17 | 2027-01-17 | Not Started
MO_A01_T027 | Support powertrain integration | Monocoque | 2027-02-07 | 2027-02-07 | Not Started
MO_A01_T028 | ANSYS 3 point bend test model | Monocoque | 2026-07-27 | 2026-08-07 | Not Started
MO_A01_T029 | ANSYS Twist Test | Monocoque | 2026-07-27 | 2026-08-24 | Not Started
MO_A01_T030 |  | Monocoque |  |  | Not Started
MO_A01_T031 |  | Monocoque |  |  | Not Started
MO_A02_T001 | Finalize monocoque CAD with points | Monocoque | 2026-09-01 | 2026-10-19 | Not Started
MO_A02_T002 | Update new monocoque CAD geometry | Monocoque | 2026-08-24 | 2026-09-30 | In Progress
MO_A02_T003 | Lock monocoque CAD points | Monocoque | 2026-10-19 | 2026-10-19 | Not Started
MO_A05_T001 | Ply Schedule Testing | Monocoque
MO_A05_T002 | Consult professional about laminates | Monocoque | 2026-08-11 | 2026-08-31 | Not Started
MO_A05_T003 | Run ANSYS twist-test ply schedule study | Monocoque | 2026-08-13 | 2026-09-11 | Not Started
MO_A05_T004 | Analyze panel test results | Monocoque | 2026-09-19 | 2026-09-19 | Not Started
MO_A05_T005 | Complete additional test-panel round | Monocoque | 2026-09-27 | 2026-10-04 | Not Started
MO_A05_T006 | Complete SES work session | Monocoque | 2026-11-05 | 2026-11-05 | Not Started
MO_A05_T007 | Continue test panels and SES documentation | Monocoque | 2026-11-09 | 2026-11-10 | Not Started
MO_A05_T008 | Lock final ply schedules | Monocoque | 2026-09-30 | 2026-11-20 | Not Started
MO_A05_T009 | Submit SES package | Monocoque | 2026-12-01 | 2026-12-01 | Not Started
MO_A05_T010 | Test Panel Jigs and Elastic Modulus | Monocoque | 2026-08-17 | 2026-08-21 | Not Started
SU_A01_T001 | Run ARG26 CG Test | Suspension | 2026-08-31 | 2026-09-05 | Not Started
SU_A01_T002 | GRIND KINEMATIC POINTS | Suspension | 2026-09-06 | 2026-09-13 | Not Started
SU_A01_T003 | Gather Design Necessary Car Data | Suspension | 2026-09-05 | 2026-09-19 | Not Started
SU_A01_T004 | test task | Suspension
SU_A02_T001 | Links manufacturing | Suspension | 2026-11-01 | 2027-01-15 | Not Started
SU_A02_T002 | Calculate Link Dimensions (Length, OD and Wall thickness) | Suspension |  |  | Not Started
SU_A02_T003 | First Round CAD of links and adapters | Suspension |  |  | Not Started
SU_A02_T004 | Optimize Upper Adapter Geometry | Suspension |  |  | Not Started
SU_A02_T005 | Order rod ends, bearings, tube stock from McMaster | Suspension |  |  | Not Started
SU_A02_T006 | Order adapters from ZTL | Suspension |  |  | Not Started
SU_A02_T007 | Machine Inserts | Suspension |  |  | Not Started
SU_A02_T008 | Manufacture push links for strain gauge installation as well as spares | Suspension |  |  | Not Started
SU_A03_T001 | Clevises manufacturing | Suspension | 2026-11-01 | 2027-01-15 | Not Started
SU_A03_T002 | Devcon Clevises | Suspension | 2027-01-21 | 2027-01-22 | Not Started
SU_A04_T001 | Rockers outsourced | Suspension | 2026-11-01 | 2027-01-15 | Not Started
SU_A05_T001 | Lock down ARB architecture | Suspension |  | 2026-09-21 | Not Started
SU_A05_T002 | First ARB CAD pass | Suspension |  | 2026-09-28 | Not Started
SU_A05_T003 | Refine torsion bar sizing, Optimise blade geometry, Validate stiffness targets | Suspension | 2026-09-28 | 2026-10-24 | Not Started
SU_A05_T004 | Design ARB Mounts and Adapters | Suspension | 2026-10-10 | 2026-10-24 | Not Started
SU_A05_T005 | ARB CAD Freeze | Suspension | 2026-10-24 | 2026-11-05 | Not Started
SU_A05_T006 | Place orders for outsourced ARB components | Suspension | 2026-11-05 | 2026-11-08 | Not Started
SU_A05_T007 | Manufacture 50% of in-house ARB components | Suspension | 2026-11-08 | 2026-12-13 | Not Started
SU_A05_T008 | Complete remaining ARB machining | Suspension | 2027-01-01 | 2027-01-15 | Not Started
SU_A05_T009 | Assemble complete ARB | Suspension | 2027-01-15 | 2027-01-18 | Not Started
SU_A05_T010 | Integrate ARB onto chassis with other suspension components | Suspension | 2027-01-18 | 2027-01-24 | Not Started
BU_A01_T001 | Professonally Wrap Car | Business | 2027-02-12 | 2027-02-15 | Not Started
BU_A01_T003 | Finalize Comp Documents | Business | 2027-05-01 | 2027-05-05
BU_A02_T001 | Publish Purchasing sheet | Business | 2026-08-28 | 2026-08-30 | In Progress
BU_A03_T001 | Upperclassmen Delibs 1 | Business | 2026-09-08 | 2026-09-08 | Not Started
BU_A03_T002 | Upperclassmen interviews | Business | 2026-09-06 | 2026-09-14
BU_A03_T003 | Project Team Fest | Business |  | 2026-09-01 | Complete
BU_A03_T004 | Info Session 1 | Business |  | 2026-09-02 | Complete
BU_A03_T005 | Info Session 2 | Business |  | 2026-09-15
BU_A03_T006 | Info Session 3 | Business |  | 2026-09-21
BU_A03_T007 | Info Session 4 | Business |  | 2026-10-07
BU_A03_T008 | First Year Delibs 1 | Business | 2026-10-17 | 2026-10-18
BU_A03_T009 | Upperclassmen Final Delibs | Business | 2026-10-12 | 2026-10-13
BU_A03_T010 | First Year Interviews | Business | 2026-10-20 | 2026-10-27
BU_A03_T011 | First Year Final Delibs | Business | 2026-10-31 | 2026-11-01
BU_A06_T001 | Finalize website | Business | 2026-08-24 | 2026-08-27 | Complete
GE_M001 | First Drive | General |  | 2027-02-07 | Not Started
CH_M001 | Chassis Drop | Chassis |  | 2027-01-25 | Not Started
PT_M001 | Powertrain Off Car Drop | Powertrain |  |  | Not Started
GE_M002 | SDR | General |  | 2026-08-16 | Complete
GE_M003 | System PDR | General |  | 2026-09-14 | In Progress
GE_M004 | PDR | General |  | 2026-09-28 | Not Started
GE_M005 | ADR | General |  | 2026-10-25 | Not Started
GE_M006 | FDR | General |  | 2026-11-25 | Not Started
PT_M002 | Order DTI Motors + Inverters | Powertrain |  | 2026-08-01 | Blocked
PT_M003 | Motor Spin | Powertrain |  |  | Not Started
PT_M004 | Motor Spin on Car | Powertrain |  |  | Not Started
PT_M005 | Steady State Powertrain | Powertrain |  |  | Not Started
GE_M007 | CAD Freeze | General |  | 2026-10-22 | Not Started
GE_M008 | Rules Released | General |  |  | Not Started
CH_M002 | Dynamic Cad done | Chassis |  | 2026-10-19 | Not Started
HV_M001 | Order pouch cells | High Voltage |  | 2026-08-30 | Not Started
HV_M002 | Order fireproof composite material | High Voltage |  | 2026-08-18 | Not Started
HV_M003 | Module parts manufactured and QCed | High Voltage |  | 2026-12-01 | Not Started
HV_M004 | Composite case manufactured | High Voltage |  | 2026-12-01 | Not Started
HV_M005 | Acc electronics components finalized (busbars inclusive) | High Voltage |  | 2026-09-21 | Not Started
AU_M001 | Autonomous Sensor + ARG26 Trackdrive | Autonomy |  | 2026-10-17 | Not Started
AU_M002 | Mapping + ARG26 Trackdrive | Autonomy |  | 2026-11-30 | Not Started
AU_M003 | Integration of DV + ARG26 | Autonomy |  | 2027-02-22 | Not Started
AU_M004 | First driverless motion through set of cones | Autonomy |  | 2027-03-08 | Not Started
AU_M005 | First full driverless autox | Autonomy |  | 2027-04-05 | Not Started
AU_M006 | Furst full driverless trackdrive | Autonomy |  | 2027-05-12 | Not Started
CO_M001 | Liquid Loop Assembled on Bench | Cooling |  | 2027-01-15 | Not Started
CO_M002 | Liquid Loop Bled on Car | Cooling |  | 2027-01-26 | Not Started
CO_M003 | Final Loop Test | Cooling |  | 2027-01-20 | Not Started
CO_M004 | Final Designs Manufactured | Cooling |  | 2027-01-13 | Not Started
CO_M005 | Final Designs Completed | Cooling |  | 2026-12-11 | Not Started
CO_M006 | Full Prototype Loop Test | Cooling |  | 2026-10-17 | Not Started
CO_M007 | Full Prototype Manufactured | Cooling |  | 2026-10-10 | Not Started
CO_M008 | Full Prototype Designs Completed | Cooling |  | 2026-09-26 | Not Started
CO_M009 | Cooling Power Requirements | Cooling |  | 2026-09-19 | Not Started
CO_M010 | Heat Rejection and Pressure Drop Targets | Cooling |  | 2026-09-11 | Not Started
CO_M011 | Liquid Loop Simulation Running | Cooling |  | 2026-09-01 | Not Started
SU_M001 | Finalize Tire Choice | Suspension |  | 2026-09-06 | Not Started
SU_M002 | Points Finalized | Suspension |  | 2026-09-15 | Not Started
SU_M003 | Link Loads Finalized | Suspension |  | 2026-09-28 | Not Started
SU_M004 | Finalize ARB stifness | Suspension |  | 2026-09-28 | Not Started
SU_M005 | Finalize Rates | Suspension |  | 2026-09-28 | Not Started
SU_M006 | Finalize WB, Front and Rear TWs, Ride Height, Weight Distribution, CG Height, Vehicle/Driver/Sprung Weights | Suspension |  | 2026-09-06 | Not Started
SU_M007 | Suspension Assembled on Car | Suspension |  | 2027-01-24 | Not Started
SU_M008 | Suspension PDR drafts done | Suspension |  | 2026-09-21 | Not Started
SU_M009 | Finalize Suspension Weight Budget | Suspension |  | 2026-09-01 | Not Started
SU_M010 | Ready to Analyze and Interpret Car Data | Suspension |  | 2026-08-30 | Not Started
GE_M009 | Finalize Drivers | General |  |  | In Progress
FW_M001 | ARG26 VD Working and Tunable | Firmware |  |  | Not Started
HV_M006 | Finalize composite TB container ply schedule per SES | High Voltage |  | 2026-10-01 | Not Started
HV_M007 | Tractive Battery electrical architechture finalized | High Voltage |  | 2026-08-26 | Not Started
HV_M008 | Laser Welder Installed in Autolab | High Voltage |  | 2026-09-01 | Not Started
HV_M009 | Tractive Battery + Inverter Packaging finalized | High Voltage |  | 2026-09-15 | Not Started
HV_M010 | Pack active cooling math finalized | High Voltage |  | 2026-09-01 | Not Started
HV_M011 | Module Discharge Rig Assembled | High Voltage |  | 2026-09-07 | Not Started
HV_M012 | Active cooling validated with module discharge rig | High Voltage |  | 2026-09-09 | Not Started
HV_M013 | Tractive Battery Modules + Container SES done | High Voltage |  | 2026-11-01 | Not Started
MO_M001 | Order Carbon for Monocoque | Monocoque |  | 2026-07-08 | Complete
MO_M002 | All Monocoque Material Ordered | Monocoque |  | 2026-08-14 | In Progress
MO_M003 | Have All Carbon (latest) | Monocoque |  | 2026-09-07 | In Progress
MO_M004 | Update and lock CAD drill point (MAY CHANGE) | Monocoque |  | 2026-10-19 | Not Started
MO_M005 | Holes Drilled into Plug | Monocoque |  |  | Not Started
MO_M006 | Plug Post Processed | Monocoque |  |  | Not Started
MO_M007 | Finish releasing one mold | Monocoque |  | 2026-11-19 | Not Started
GE_M010 | ARG26 First Drive | General |  | 2026-09-05 | Not Started
MO_M008 | Ply schedules FROZEN | Monocoque |  | 2026-11-20 | Not Started
MO_M009 | SES Submitted | Monocoque |  |  | Not Started
MO_M010 | Monocoque Drop | Monocoque |  | 2027-01-18 | Not Started
AU_M007 | Sensors and Compute Ordered | Autonomy |  | 2026-09-29 | Blocked
GE_M011 | ARG27 Second Drive | General |  | 2027-03-14 | Not Started
GE_M012 | Fully rules compliant car | General |  | 2027-04-01 | Blocked
AE_M001 | CFD Freeze | Aerodynamics |  |  | Not Started
AE_M002 | Finalize Aero Targets | Aerodynamics |  |  | In Progress
AE_M003 | Plugs and Tooling Made | Aerodynamics |  |  | Not Started
AE_M004 | Mounted to car | Aerodynamics |  |  | Not Started
ER_M001 | Ergo Points Finalized | Ergonomics |  | 2026-09-30 | Not Started
LV_M001 | Altium library groundwork finished | Low Voltage |  |  | In Progress
LV_M002 | First revs schematics done | Low Voltage |  | 2026-08-17 | In Progress
LV_M003 | First revs layout done | Low Voltage |  | 2026-09-09 | Not Started
LV_M004 | First revs ordered | Low Voltage |  | 2026-09-10 | Not Started
LV_M005 | First revs tested | Low Voltage |  | 2026-09-28 | Not Started
LV_M006 | Precharge tested in loop | Low Voltage |  | 2027-01-07 | Not Started
LV_M007 | BMS Children LV/HV tested | Low Voltage |  | 2027-01-08 | Not Started
LV_M008 | BMS Children integrated onto modules | Low Voltage |  | 2027-01-09 | Not Started
LV_M009 | Shutdown circuit closed | Low Voltage |  | 2027-01-15 | Not Started
LV_M010 | LV Harness ICDs finished | Low Voltage |  | 2026-10-11 | Not Started
LV_M011 | Enclosures finalized | Low Voltage |  | 2026-10-22 | Not Started
LV_M012 | Power budget estimated | Low Voltage |  | 2026-10-01 | Not Started
LV_M013 | LV Harness Sensors finalized | Low Voltage |  | 2026-10-11 | Not Started
ER_M002 | Steering System Components Ordered | Ergonomics |  | 2026-11-13 | Not Started
ER_M003 | All Driver Loads Redefined | Ergonomics |  | 2026-09-18 | Not Started
CO_M012 | Mock Endurance ARG26 | Cooling | 2026-08-31 | 2026-09-04 | Not Started
CO_M013 | Liquid Loop Installed on Car | Cooling | 2027-01-15 | 2027-01-22 | Not Started
ER_M004 | Mock Cockpit Template Passed | Ergonomics | 2027-02-01 | 2027-02-12 | Not Started
FW_M002 | ARG26 VD Fully Tested | Firmware |  | 2026-10-25 | Not Started
FW_M003 | BMS Code Validated | Firmware |  |  | Not Started
MO_M011 | Molds Complete and SES Submission Confirmed | Monocoque | 2026-12-06 | 2026-12-06 | Not Started
MO_M012 | Monocoque Released from Molds | Monocoque | 2027-01-18 | 2027-01-18 | Not Started
MO_M013 | Chassis Integration Complete | Monocoque | 2027-01-29 | 2027-01-29 | Not Started
MO_M014 | Rolling Chassis | Monocoque | 2027-02-04 | 2027-02-04 | Not Started
MO_M015 | First Drive | Monocoque | 2027-02-14 | 2027-02-14 | Not Started
SU_M011 | First Suspension Assembly | Suspension | 2027-01-18 | 2027-01-21 | Not Started
BU_M001 | Upperclassman Apps Due | Business |  | 2026-09-01 | In Progress
BU_M002 | Upperclassman Offer | Business |  | 2026-09-16
BU_M003 | First Year Offer | Business |  | 2026-11-02
GE_M013 | Autolab Clean Up | General |  | 8/

## GE Tasks
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
GE_A00_T001 | Subteam part designer sprints | General | 2026-08-31 | 2026-09-04 | In Progress |  |  | High |  |  |  | A00 - General
GE_A00_T002 | Tuning for Toronto Shootout | General | 2026-09-21 | 2026-09-30 | Not Started |  | Caroline Moskal | High |  |  |  | A00 - General
GE_A00_T003 | Pack for Toronto Shootout | General | 2026-10-01 | 2026-10-02 | Not Started |  | Caroline Moskal | High |  |  |  | A00 - General
GE_A00_T004 | Tech inspection for Toronto Shootout | General | 2026-09-28 | 2026-09-30 | Not Started |  | Caroline Moskal | High | GE_A00_T002 |  |  | A00 - General
|  | General | [9 empty] | A00 - General
|  | General | [9 empty] | A00 - General
|  | General | [9 empty] | A00 - General
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
GE_A01_T001 | Mech Check outs for ARG26 | Chassis | 2026-08-30 | 2026-09-01 | Complete |  | Nicholas Gavalas | High |  |  |  | A01 - Chassis
GE_A01_T002 | ARG26 Bolt Check | Chassis | 2026-08-30 | 2026-08-31 | In Progress |  | Nicholas Gavalas | High |  |  |  | A01 - Chassis
|  | Chassis | [9 empty] | A01 - Chassis
|  | Chassis | [9 empty] | A01 - Chassis
|  | Chassis | [9 empty] | A01 - Chassis
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
GE_A02_T001 | EV Check outs for ARG26 | Powertrain | 2026-08-31 | 2026-09-02 | Not Started |  | Will Hutter | High | GE_A01_T002 |  |  | A02 - Powertrain
GE_A02_T002 | Sensor integration on ARG26 | Powertrain | 2026-09-01 | 2026-09-05 | Not Started |  | Will Hutter | High |  |  |  | A02 - Powertrain
GE_A02_T003 | Charging ARG26 pack | Powertrain | 2026-09-02 | 2026-09-04 | Complete |  | Will Hutter | High |  |  |  | A02 - Powertrain
|  | Powertrain | [9 empty] | A02 - Powertrain
|  | Powertrain | [9 empty] | A02 - Powertrain

## HV Tasks
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
HV_A01_T001 | test task | High Voltage | [9 empty] | A01 - High Voltage
|  | High Voltage | [9 empty] | A01 - High Voltage
|  | High Voltage | [9 empty] | A01 - High Voltage
|  | High Voltage | [9 empty] | A01 - High Voltage
|  | High Voltage | [9 empty] | A01 - High Voltage
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | High Voltage | [9 empty] | A02 - Modules
|  | High Voltage | [9 empty] | A02 - Modules
|  | High Voltage | [9 empty] | A02 - Modules
|  | High Voltage | [9 empty] | A02 - Modules
|  | High Voltage | [9 empty] | A02 - Modules
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | High Voltage | [9 empty] | A03 - Case
|  | High Voltage | [9 empty] | A03 - Case
|  | High Voltage | [9 empty] | A03 - Case
|  | High Voltage | [9 empty] | A03 - Case
|  | High Voltage | [9 empty] | A03 - Case
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | High Voltage | [9 empty] | A04 - Accumulator Electronics
|  | High Voltage | [9 empty] | A04 - Accumulator Electronics
|  | High Voltage | [9 empty] | A04 - Accumulator Electronics
|  | High Voltage | [9 empty] | A04 - Accumulator Electronics
|  | High Voltage | [9 empty] | A04 - Accumulator Electronics
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | High Voltage | [9 empty] | A05 - Inverter Enclosure
|  | High Voltage | [9 empty] | A05 - Inverter Enclosure
|  | High Voltage | [9 empty] | A05 - Inverter Enclosure
|  | High Voltage | [9 empty] | A05 - Inverter Enclosure
|  | High Voltage | [9 empty] | A05 - Inverter Enclosure
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | High Voltage | [9 empty] | A06 - Powerhouse
|  | High Voltage | [9 empty] | A06 - Powerhouse
|  | High Voltage | [9 empty] | A06 - Powerhouse
|  | High Voltage | [9 empty] | A06 - Powerhouse
|  | High Voltage | [9 empty] | A06 - Powerhouse
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | High Voltage | [9 empty] | A07 - Control Panel
|  | High Voltage | [9 empty] | A07 - Control Panel
|  | High Voltage | [9 empty] | A07 - Control Panel
|  | High Voltage | [9 empty] | A07 - Control Panel
|  | High Voltage | [9 empty] | A07 - Control Panel
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | High Voltage | [9 empty] | A08 - RTML and TSSI
|  | High Voltage | [9 empty] | A08 - RTML and TSSI
|  | High Voltage | [9 empty] | A08 - RTML and TSSI
|  | High Voltage | [9 empty] | A08 - RTML and TSSI
|  | High Voltage | [9 empty] | A08 - RTML and TSSI
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | High Voltage | [9 empty] | A09 - Other High Voltage
|  | High Voltage | [9 empty] | A09 - Other High Voltage
|  | High Voltage | [9 empty] | A09 - Other High Voltage
|  | High Voltage | [9 empty] | A09 - Other High Voltage
|  | High Voltage | [9 empty] | A09 - Other High Voltage

## LV Tasks
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
LV_A01_T001 | Altium library basics finished | Low Voltage | 2026-07-13 | 2026-08-09 | Review |  | Arielle Huang | High |  | Commonized components |  | A01 - Low Voltage
|  | Low Voltage | [9 empty] | A01 - Low Voltage
|  | Low Voltage | [9 empty] | A01 - Low Voltage
|  | Low Voltage | [9 empty] | A01 - Low Voltage
|  | Low Voltage | [9 empty] | A01 - Low Voltage
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Low Voltage | [9 empty] | A02 - Harness
|  | Low Voltage | [9 empty] | A02 - Harness
|  | Low Voltage | [9 empty] | A02 - Harness
|  | Low Voltage | [9 empty] | A02 - Harness
|  | Low Voltage | [9 empty] | A02 - Harness
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Low Voltage | [9 empty] | A03 - ECU
|  | Low Voltage | [9 empty] | A03 - ECU
|  | Low Voltage | [9 empty] | A03 - ECU
|  | Low Voltage | [9 empty] | A03 - ECU
|  | Low Voltage | [9 empty] | A03 - ECU
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
LV_A04_T001 | Design first rev of BMS Child | Low Voltage | 2026-08-01 | 2026-09-01 | In Progress |  | Sam Hunter | High |  | PCB ordered |  | A04 - BMS Child
LV_A04_T002 | Test/debug first rev of BMS child | Low Voltage | 2026-09-07 | 2026-09-21 | Not Started |  | Sam Hunter | High |  | Test report/results + required modifications | Dependent on LV006, couldn't select it | A04 - BMS Child
LV_A04_T003 | Validate communication between BMS child/mother | Low Voltage | 2026-09-21 | 2026-10-01 | Not Started |  | Sam Hunter | High |  | Functional basic BSM system | Timeline dependent on LV007, couldn't select it. Also Natsu is a co-owner, couldn't add him. | A04 - BMS Child
LV_A04_T004 | Design final rev of BMS child for module integration | Low Voltage | 2026-10-01 | 2026-11-16 | Not Started |  | Sam Hunter | High |  | PCB ordered | Dependent on LV008 | A04 - BMS Child
LV_A04_T005 | Test final rev of BMS child | Low Voltage | 2026-11-23 | 2026-12-01 | Not Started |  | Sam Hunter | High |  | Functioning child board | Dependent on LV009 | A04 - BMS Child
LV_A04_T006 | Bring up + validate all BMS children + spares | Low Voltage | 2026-12-01 | 2027-01-15 | Not Started |  | Sam Hunter | High |  | Working BMS system | Dependent on LV010 | A04 - BMS Child
|  | Low Voltage | [9 empty] | A04 - BMS Child
|  | Low Voltage | [9 empty] | A04 - BMS Child
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Low Voltage | [9 empty] | A05 - ACU
|  | Low Voltage | [9 empty] | A05 - ACU
|  | Low Voltage | [9 empty] | A05 - ACU
|  | Low Voltage | [9 empty] | A05 - ACU
|  | Low Voltage | [9 empty] | A05 - ACU
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
LV_A06_T001 | Shutdown circuit closes | Low Voltage |  |  | Not Started |  | Arielle Huang Valerie Shu |  |  |  |  | A06 - Shutdown
|  | Low Voltage | [9 empty] | A06 - Shutdown
|  | Low Voltage | [9 empty] | A06 - Shutdown
|  | Low Voltage | [9 empty] | A06 - Shutdown
|  | Low Voltage | [9 empty] | A06 - Shutdown
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
LV_A07_T001 | Precharge and discharge validated | Low Voltage |  |  | Not Started |  | Arielle Huang Nathaniel Su |  |  |  |  | A07 - Discharge
|  | Low Voltage | [9 empty] | A07 - Discharge
|  | Low Voltage | [9 empty] | A07 - Discharge
|  | Low Voltage | [9 empty] | A07 - Discharge
|  | Low Voltage | [9 empty] | A07 - Discharge
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
LV_A08_T001 | Get PDM08 and ACC3s | Low Voltage | 2026-08-09 | 2026-09-07 | Not Started | [6 empty] | A08 - PDU
LV_A08_T002 | HV DCDC/LV DCDC Choice | Low Voltage |  |  | In Progress |  | Arielle Huang Sean Li |  |  | HV DCDC locked | For PDU, depends on cooling | A08 - PDU
LV_A08_T003 | Design first rev of PDU | Low Voltage | 2026-08-05 | 2026-09-05 | Not Started |  | Sean Li | High |  | PCB ordered | dependent on cooling pump/radiator/fan selection | A08 - PDU
|  | Low Voltage | [9 empty] | A08 - PDU
|  | Low Voltage | [9 empty] | A08 - PDU
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
LV_A09_T001 | Dash multple screens | Low Voltage |  |  | Not Started |  | Yifan Li Keira Chen |  |  |  |  | A09 - Dash
LV_A09_T002 | Design first rev of Dash | Low Voltage |  |  | Planned |  | Keira Chen | Medium |  | PCB ordered |  | A09 - Dash
LV_A09_T003 | Order Dash components | Low Voltage |  |  | Not Started |  | Keira Chen | Medium |  | components arrive |  | A09 - Dash
LV_A09_T004 | Bring up + Test Dash rev1 | Low Voltage |  |  | Not Started |  | Keira Chen | Medium |  | working Dash board |  | A09 - Dash
LV_A09_T005 | Dash harnessing | Low Voltage |  |  | Not Started |  | Keira Chen | Medium |  | harness is complete |  | A09 - Dash
LV_A09_T006 | Dash integration | Low Voltage |  |  | Not Started |  | Keira Chen | Medium |  | dash is on car and working |  | A09 - Dash
LV_A09_T007 | Bring up final rev Dash spares | Low Voltage |  |  | Not Started |  | Keira Chen | Medium |  | spares are available |  | A09 - Dash
|  | Low Voltage | [9 empty] | A09 - Dash
|  | Low Voltage | [9 empty] | A09 - Dash
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Low Voltage | [9 empty] | A10 - Other Low Voltage
|  | Low Voltage | [9 empty] | A10 - Other Low Voltage
|  | Low Voltage | [9 empty] | A10 - Other Low Voltage
|  | Low Voltage | [9 empty] | A10 - Other Low Voltage
|  | Low Voltage | [9 empty] | A10 - Other Low Voltage

## CO Tasks
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Cooling | [9 empty] | A01 - Cooling
|  | Cooling | [9 empty] | A01 - Cooling
|  | Cooling | [9 empty] | A01 - Cooling
|  | Cooling | [9 empty] | A01 - Cooling
|  | Cooling | [9 empty] | A01 - Cooling
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
CO_A02_T002 | Run full liquid loop pressure drop test | Cooling |  |  | Not Started |  | Ilana Yousuf | Medium |  |  |  | A02 - Liquid Loop
CO_A02_T009 | Identify system parameters w/ hand calcs and data |  |  |  | Not Started |  | Ilana Yousuf | High |  |  |  | A02 - Liquid Loop
CO_A02_T003 | Determine necessary radiator and fan specifications | Cooling | 2026-09-08 | 2026-09-11 | Not Started |  | Ilana Yousuf | High |  |  |  | A02 - Liquid Loop
CO_A02_T004 | Order stock radiator for testing | Cooling | 2026-09-15 | 2026-09-20 | Not Started |  | Ilana Yousuf | Medium |  |  |  | A02 - Liquid Loop
CO_A02_T005 | Test and confirm geometry/layout | Cooling | 2026-09-15 | 2026-09-25 | Not Started |  | Ilana Yousuf | Medium |  |  |  | A02 - Liquid Loop
CO_A02_T001 | PRIORITY: order custom radiator | Cooling | 2026-09-11 | 2026-09-30 | Not Started |  | Ilana Yousuf | High |  |  |  | A02 - Liquid Loop
CO_A02_T006 | Manufacture liquid loop prototype | Cooling | 2026-10-01 | 2026-10-08 | Not Started |  | Ilana Yousuf | Medium |  |  |  | A02 - Liquid Loop
CO_A02_T007 | Conduct tests and collect data for pressure drop and heat rejection | Cooling | 2026-10-10 | 2026-10-17 | Not Started |  | Ilana Yousuf | High |  |  |  | A02 - Liquid Loop
CO_A02_T008 | Assemble final liquid loop on bench | Cooling | 2027-01-04 | 2027-01-15 | Not Started |  | Ilana Yousuf | High |  |  |  | A02 - Liquid Loop
CO_A02_T010 | Calibrate Temp sensors and put on car for endurance testing | Cooling | 2026-09-04 | 2026-09-04 | Not Started |  |  | High |  |  |  | A02 - Liquid Loop
|  | Cooling | [9 empty] | A02 - Liquid Loop
|  | Cooling | [9 empty] | A02 - Liquid Loop
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
CO_A03_T001 | Run motor sleeve heat rejection + flow test | Cooling |  |  |  |  | Usanbolor Amartuvshin | Medium |  |  |  | A03 - Cooling Sleeve
CO_A03_T002 | Cooling Sleeve ANSYS Model | Cooling |  |  |  |  | Usanbolor Amartuvshin | High |  | Acc architecture finalized prerec |  | A03 - Cooling Sleeve
CO_A03_T003 | Determine Cooling Sleeve Sealing Strategy | Cooling | 2026-08-26 |  | In Progress |  | Usanbolor Amartuvshin | High |  |  |  | A03 - Cooling Sleeve
|  | Cooling | [9 empty] | A03 - Cooling Sleeve
|  | Cooling | [9 empty] | A03 - Cooling Sleeve
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
CO_A04_T001 | Acc Cooling ANSYS Model | Cooling |  |  |  |  | Theresa Franklin | High |  |  |  | A04 - Accumulator Cooling
CO_A04_T002 | Base Simulation for Acc Cooling + Feasible Configurations | Cooling | 2026-08-26 | 2026-08-30 | In Progress |  | Theresa Franklin | High |  |  |  | A04 - Accumulator Cooling
CO_A04_T003 | Preliminary Acc Cooling Testing | Cooling | 2026-08-30 | 2026-09-10 | In Progress |  | Theresa Franklin | High |  |  |  | A04 - Accumulator Cooling
|  | Cooling | [9 empty] | A04 - Accumulator Cooling
|  | Cooling | [9 empty] | A04 - Accumulator Cooling
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Cooling | [9 empty] | A05 - Other Cooling
|  | Cooling | [9 empty] | A05 - Other Cooling
|  | Cooling | [9 empty] | A05 - Other Cooling
|  | Cooling | [9 empty] | A05 - Other Cooling
|  | Cooling | [9 empty] | A05 - Other Cooling

## FW Tasks
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
FW_A01_T001 | ARG27 VD flashed on car | Firmware |  |  |  |  | Amrita Talwar |  |  |  |  | A01 - Firmware
|  | Firmware | [9 empty] | A01 - Firmware
|  | Firmware | [9 empty] | A01 - Firmware
|  | Firmware | [9 empty] | A01 - Firmware
|  | Firmware | [9 empty] | A01 - Firmware
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
FW_A02_T001 | SOC drawn out implementation | Firmware |  | 2026-09-28 | In Progress |  | Nathaniel Su | Medium |  |  |  | A02 - BMS Code
FW_A02_T002 | ACU bring up testing branch formed | Firmware |  | 2026-09-28 | Not Started |  | Nathaniel Su | High |  |  |  | A02 - BMS Code
FW_A02_T003 | SOC working on arg26 | Firmware |  | 2026-10-25 | Not Started |  | Nathaniel Su | High |  |  |  | A02 - BMS Code
FW_A02_T004 | LAMBMS what needs to change ready | Firmware |  | 2026-10-25 | Not Started |  | Nathaniel Su | Medium |  |  |  | A02 - BMS Code
FW_A02_T005 | Serial monitor clean up | Firmware |  | 2026-10-25 | Not Started |  | Nathaniel Su | Medium |  |  |  | A02 - BMS Code
FW_A02_T006 | SOC on arg27 | Firmware |  | 2026-11-25 | Not Started |  | Nathaniel Su | High |  |  |  | A02 - BMS Code
|  | Firmware | [9 empty] | A02 - BMS Code
|  | Firmware | [9 empty] | A02 - BMS Code
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
FW_A03_T001 | RTOS implemented on ARG26 | Firmware |  | 2026-10-25 | Not Started |  | Amrita Talwar | Medium |  |  |  | A03 - ECU Code
FW_A03_T002 | RTOS MVP | Firmware |  | 2026-09-28 | Not Started |  | Shadman Syed |  |  |  |  | A03 - ECU Code
FW_A03_T003 | RTOS testing done | Firmware |  | 2026-10-04 | Not Started |  | Shadman Syed |  |  |  |  | A03 - ECU Code
|  | Firmware | [9 empty] | A03 - ECU Code
|  | Firmware | [9 empty] | A03 - ECU Code
|  | Firmware | [9 empty] | A03 - ECU Code
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
FW_A04_T001 | Lanch control simple model | Firmware |  | 2026-09-28 | Not Started |  | Xinyuan (Yolanda) Zhou | Critical |  |  |  | A04 - Active VD Controls
FW_A04_T002 | Power limiting simple model | Firmware |  | 2026-09-28 | Not Started |  | Xinyuan (Yolanda) Zhou | Critical |  |  |  | A04 - Active VD Controls
FW_A04_T003 | Regen simple model | Firmware |  | 2026-09-28 | Not Started |  | Xinyuan (Yolanda) Zhou | Critical |  |  |  | A04 - Active VD Controls
FW_A04_T004 | Torque Vectoring simple model | Firmware |  | 2026-10-25 | Not Started |  | Xinyuan (Yolanda) Zhou | Critical |  |  |  | A04 - Active VD Controls
FW_A04_T005 | Power limiting complex model | Firmware |  | 2026-11-25 | Not Started |  | Xinyuan (Yolanda) Zhou | High |  |  |  | A04 - Active VD Controls
FW_A04_T006 | Regen Complex Model | Firmware |  | 2026-11-25 | Not Started |  | Xinyuan (Yolanda) Zhou | High |  |  |  | A04 - Active VD Controls
FW_A04_T007 | Torque Vectoring Complex Model | Firmware |  | 2027-01-14 | Not Started |  | Xinyuan (Yolanda) Zhou | High |  |  | subject to change depending on JanMan | A04 - Active VD Controls
FW_A04_T008 | Launch Control Complex Modeling | Firmware |  | 2027-01-14 | Not Started |  | Xinyuan (Yolanda) Zhou | High |  |  | subject to change depending on JanMan | A04 - Active VD Controls
FW_A04_T009 | VD DTI motor Comparision | Firmware |  | 2026-09-28 | Not Started |  | Xinyuan (Yolanda) Zhou | High |  |  |  | A04 - Active VD Controls
FW_A04_T010 | VD testing plan for all four compontents | Firmware |  | 2026-09-28 | [7 empty] | A04 - Active VD Controls
FW_A04_T013 | Simplified RTOS implementation for ECU |  |  | 2026-09-15 | In Progress |  | Shadman Syed | Critical |  |  |  | A04 - Active VD Controls
FW_A04_T014 | Full RTOS port of ECU |  |  | 2026-09-26 | Blocked |  | Shadman Syed | Critical | FW_A04_T013 |  |  | A04 - Active VD Controls
FW_A04_T015 | Debug RTOS port for concurrency issues |  |  | 2026-10-03 | Not Started |  |  | High |  |  |  | A04 - Active VD Controls
FW_A04_T016 | Implementing the VD simple models | Firmware | 2026-10-05 | 2026-10-31 | Not Started |  |  | High | FW_A04_T004 |  |  | A04 - Active VD Controls
|  | Firmware | [9 empty] | A04 - Active VD Controls
|  | Firmware | [9 empty] | A04 - Active VD Controls
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
FW_A05_T001 | Diagrams done, Changes to Dash finialized | Firmware |  | 2026-09-28 | Not Started |  | Yifan Li |  |  |  |  | A05 - Dash Firmware
FW_A05_T002 | Arg26 Dash fixed | Firmware |  | 2026-10-25 | Not Started |  | Yifan Li |  |  |  |  | A05 - Dash Firmware
FW_A05_T003 | CanLib integreated to dash | Firmware |  | 2026-11-25 | Not Started |  | Yifan Li |  |  |  |  | A05 - Dash Firmware
FW_A05_T004 | dash code done | Firmware |  | 2027-01-14 | Not Started |  | Yifan Li |  |  |  |  | A05 - Dash Firmware
FW_A05_T005 | website done | Firmware |  | 2027-01-14 | Not Started |  | Yifan Li |  |  |  |  | A05 - Dash Firmware
FW_A05_T007 | Power limiting Logging off car | Firmware |  | 2026-09-28 | Not Started |  | Yifan Li |  |  |  |  | A05 - Dash Firmware
FW_A05_T006 |  | Firmware | [9 empty] | A05 - Dash Firmware
|  | Firmware | [9 empty] | A05 - Dash Firmware
|  | Firmware | [9 empty] | A05 - Dash Firmware
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
FW_A06_T001 | Telem website working | Firmware |  |  |  |  | Amrita Talwar |  |  |  |  | A06 - Other Firmware
|  | Firmware | [9 empty] | A06 - Other Firmware
|  | Firmware | [9 empty] | A06 - Other Firmware
|  | Firmware | [9 empty] | A06 - Other Firmware
|  | Firmware | [9 empty] | A06 - Other Firmware

## AU Tasks
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Autonomy | [9 empty] | A01 - Autonomy
|  | Autonomy | [9 empty] | A01 - Autonomy
|  | Autonomy | [9 empty] | A01 - Autonomy
|  | Autonomy | [9 empty] | A01 - Autonomy
|  | Autonomy | [9 empty] | A01 - Autonomy
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
AU_A02_T001 | Design modular ARG26 sensor mount(s) | Autonomy |  | 2026-09-09 | Not Started | AU_M001 | Teddy Duncker | Critical |  |  |  | A02 - Autonomy Mechanical
AU_A02_T002 | Calculate drag of sensor choices for Nicholas | Autonomy |  |  | Not Started |  | Teddy Duncker | Low |  |  |  | A02 - Autonomy Mechanical
AU_A02_T003 | Build steering actuator system | Autonomy |  |  | Not Started | AU_M004 | Teddy Duncker | Critical |  |  |  | A02 - Autonomy Mechanical
AU_A02_T004 | Integrate sensor mount onto ARG26 | Autonomy |  |  | Not Started | AU_M001 | Teddy Duncker | High |  |  |  | A02 - Autonomy Mechanical
AU_A02_T005 |  | Autonomy | [9 empty] | A02 - Autonomy Mechanical
|  | Autonomy | [9 empty] | A02 - Autonomy Mechanical
|  | Autonomy | [9 empty] | A02 - Autonomy Mechanical
|  | Autonomy | [9 empty] | A02 - Autonomy Mechanical
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
AU_A03_T001 | Centerline vs. optimized analysis | Autonomy |  |  | Not Started |  | Sayee Edekar | Low |  |  | Not required | A03 - Path Planning and Following
AU_A03_T002 | Steering actuator step response transfer function generation | Autonomy |  |  | Not Started | AU_M004 | Sayee Edekar | High | AU_A02_T003 |  |  | A03 - Path Planning and Following
AU_A03_T003 | Minimum lookahead & FOV analysis | Autonomy |  | 2026-07-26 | Complete | AU_M007 | Teddy Duncker | Critical |  |  |  | A03 - Path Planning and Following
AU_A03_T004 | Model Predictive Control parameters calculated | Autonomy |  | 2026-11-01 | Not Started | AU_M004 | Sayee Edekar | Critical |  |  |  | A03 - Path Planning and Following
|  | Autonomy | [9 empty] | A03 - Path Planning and Following
|  | Autonomy | [9 empty] | A03 - Path Planning and Following
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
AU_A04_T001 | Camera choice | Autonomy |  |  | Complete | AU_M007 | Teddy Duncker | Critical |  |  |  | A04 - Sensors and Harnessing
AU_A04_T002 | LiDAR choice | Autonomy |  |  | Complete | AU_M007 | Teddy Duncker | Critical |  |  |  | A04 - Sensors and Harnessing
|  | Autonomy | [9 empty] | A04 - Sensors and Harnessing
|  | Autonomy | [9 empty] | A04 - Sensors and Harnessing
|  | Autonomy | [9 empty] | A04 - Sensors and Harnessing
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
AU_A05_T001 | Compute module choice | Autonomy |  | 2026-08-31 | Complete | AU_M007 | Benson Zhuo | Critical |  |  |  | A05 - Compute and Hardware
AU_A05_T002 | Figure out what PCBs will be needed for safety compliance autonomy integration to ARG26 | Autonomy |  | 2026-08-28 | Complete | AU_M004 | Benson Zhuo | High |  |  |  | A05 - Compute and Hardware
AU_A05_T003 | Place order for DCU | Autonomy |  | 2026-09-18 | Not Started | AU_M004 | Benson Zhuo | Medium |  |  |  | A05 - Compute and Hardware
AU_A05_T004 | Bring up and test DCU | Autonomy |  | 2026-10-09 | Not Started | AU_M004 | Benson Zhuo | Medium | AU_A05_T003 |  |  | A05 - Compute and Hardware
AU_A05_T005 | Order RAM, storage, CAN PCIe card | Autonomy |  | 2026-09-07 | Not Started | AU_M007 | Benson Zhuo | Critical | AU_A05_T001 |  |  | A05 - Compute and Hardware
|  | Autonomy | [9 empty] | A05 - Compute and Hardware
|  | Autonomy | [9 empty] | A05 - Compute and Hardware
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
AU_A06_T001 | Buy Cones & Reflective Tape | Autonomy |  | 2026-09-07 | In Progress | AU_M001 | Emily Ng | High |  |  |  | A06 - Perception and Data Interface
AU_A06_T002 | Get Camera Data off of the Hteng Vishi to Linux/ROS | Autonomy |  | 2026-09-09 | Not Started | AU_M001 | Emily Ng | Critical |  |  |  | A06 - Perception and Data Interface
AU_A06_T003 | Determine required peripherals for putting cameras on car | Autonomy |  | 2026-09-09 | Not Started | AU_M001 | Emily Ng | Medium |  |  |  | A06 - Perception and Data Interface
AU_A06_T004 | CNN/YOLO/other detector for cone color type in autolab | Autonomy |  | 2026-09-16 | Not Started | AU_M002 | Emily Ng | High |  |  |  | A06 - Perception and Data Interface
AU_A06_T005 | Get Data off of the LiDAR | Autonomy |  | 2026-09-30 | Not Started | AU_M001 | Emily Ng | Critical |  |  | Will depend on LiDAR delivery date | A06 - Perception and Data Interface
AU_A06_T007 | Implement ground removal algorithm | Autonomy |  | 2026-10-10 | Not Started | AU_M002 | Emily Ng | High |  |  |  | A06 - Perception and Data Interface
AU_A06_T006 | Implement point clustering algorithm for LiDAR cone detection | Autonomy |  | 2026-10-15 | Not Started | AU_M002 | Emily Ng | High |  |  |  | A06 - Perception and Data Interface
|  | Autonomy | [9 empty] | A06 - Perception and Data Interface
|  | Autonomy | [9 empty] | A06 - Perception and Data Interface
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
AU_A07_T001 | SITL suite | Autonomy |  | 2027-01-20 | Not Started | AU_M004 | Emily Ng | Low |  |  |  | A07 - Software Pipeline
|  | Autonomy | [9 empty] | A07 - Software Pipeline
|  | Autonomy | [9 empty] | A07 - Software Pipeline
|  | Autonomy | [9 empty] | A07 - Software Pipeline
|  | Autonomy | [9 empty] | A07 - Software Pipeline
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Autonomy | [9 empty] | A08 - Other Autonomy
|  | Autonomy | [9 empty] | A08 - Other Autonomy
|  | Autonomy | [9 empty] | A08 - Other Autonomy
|  | Autonomy | [9 empty] | A08 - Other Autonomy
|  | Autonomy | [9 empty] | A08 - Other Autonomy

## AE Tasks
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
AE_A01_T001 | Aero Mounted | Aerodynamics | 2027-01-01 | 2027-03-01 | Not Started |  | Kathryn Ainley-Zoll | High |  | Aero components mounted and integrated | Milestone/completion activity | A01 - Aerodynamics
AE_A01_T002 | Manufacture Aero, Pt 1 | Aerodynamics |  |  |  |  | Kathryn Ainley-Zoll | High |  | Manufactured aerodynamic components |  | A01 - Aerodynamics
AE_A01_T003 | Finalize Aero Targets | Aerodynamics | 2026-08-01 | 2026-08-10 | In Progress |  | Kathryn Ainley-Zoll | High |  | Finalized aerodynamic targets |  | A01 - Aerodynamics
AE_A01_T004 | Post PDR Alum Outreach | Aerodynamics | 2026-09-28 | 2026-10-03 | Not Started |  | Kathryn Ainley-Zoll | Medium |  | Alumni outreach completed |  | A01 - Aerodynamics
AE_A01_T005 | Surface Modeling Training | Aerodynamics | 2026-08-24 | 2026-08-28 | Complete |  | Kathryn Ainley-Zoll | Medium |  | Completed surface modeling training |  | A01 - Aerodynamics
AE_A01_T006 | Mounting Finalized | Aerodynamics | 2026-08-01 | 2026-09-28 | Not Started |  | Kathryn Ainley-Zoll | High |  | Finalized mounting design |  | A01 - Aerodynamics
AE_A01_T007 | Mounting Manufactured | Aerodynamics | 2026-11-01 | 2026-11-30 | Not Started |  | Kathryn Ainley-Zoll | High |  | Manufactured mounting hardware |  | A01 - Aerodynamics
AE_A01_T008 | On-Car Testing | Aerodynamics | 2027-01-01 | 2027-05-01 | Not Started |  | Kathryn Ainley-Zoll | High |  | On-car aero testing results |  | A01 - Aerodynamics
AE_A01_T009 | CFD Analysis Training | Aerodynamics | 2026-08-31 | 2026-09-04 | In Progress |  | Kathryn Ainley-Zoll | High |  | Completed training |  | A01 - Aerodynamics
|  | Aerodynamics | [9 empty] | A01 - Aerodynamics
|  | Aerodynamics | [9 empty] | A01 - Aerodynamics
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
AE_A02_T001 | Airfoils selected for wings | Aerodynamics | 2026-09-28 | 2026-09-29 | Not Started |  | Lilly Varon | High |  | Final airfoil selection |  | A02 - Front Wing
AE_A02_T002 | Tooling for Wings and UT Made | Aerodynamics | 2026-11-01 | 2026-11-14 | Not Started |  | Lilly Varon | High |  | Wing and undertray tooling |  | A02 - Front Wing
AE_A02_T003 | Manufacturing for Wings and UT | Aerodynamics | 2027-01-01 | 2027-02-01 | Not Started |  | Lilly Varon | High |  | Manufactured wings and undertray |  | A02 - Front Wing
|  | Aerodynamics | [9 empty] | A02 - Front Wing
|  | Aerodynamics | [9 empty] | A02 - Front Wing
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
AE_A03_T001 | Airfoils selected for wings | Aerodynamics | 2026-09-28 | 2026-09-29 | Not Started |  | Montserrat McCoy | High |  | Final airfoil selection |  | A03 - Rear Wing
AE_A03_T002 | Tooling for Wings and UT Made | Aerodynamics | 2026-11-01 | 2026-11-14 | Not Started |  | Montserrat McCoy | High |  | Wing and undertray tooling |  | A03 - Rear Wing
AE_A03_T003 | Manufacturing for Wings and UT | Aerodynamics | 2027-01-01 | 2027-02-01 | Not Started |  | Montserrat McCoy | High |  | Manufactured wings and undertray |  | A03 - Rear Wing
|  | Aerodynamics | [9 empty] | A03 - Rear Wing
|  | Aerodynamics | [9 empty] | A03 - Rear Wing
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
AE_A04_T001 | Tooling for Wings and UT Made | Aerodynamics | 2026-11-01 | 2026-11-14 | Not Started |  | Aidan Moller | High |  | Wing and undertray tooling |  | A04 - Undertray
AE_A04_T002 | Manufacturing for Wings and UT | Aerodynamics | 2027-01-01 | 2027-02-01 | Not Started |  | Aidan Moller | High |  | Manufactured wings and undertray |  | A04 - Undertray
|  | Aerodynamics | [9 empty] | A04 - Undertray
|  | Aerodynamics | [9 empty] | A04 - Undertray
|  | Aerodynamics | [9 empty] | A04 - Undertray
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
AE_A05_T001 | Plugs for Nosecone and Sidepods Made | Aerodynamics | 2026-10-16 | 2026-10-24 | Not Started |  | Junseok Kang | High |  | Nosecone and sidepod plugs |  | A05 - Auxiliary Elements
AE_A05_T002 | Manufacturing for Nosecone and Sidepod | Aerodynamics | 2026-10-24 | 2027-03-01 | Not Started |  | Junseok Kang | High |  | Manufactured nosecone and sidepod |  | A05 - Auxiliary Elements
|  | Aerodynamics | [9 empty] | A05 - Auxiliary Elements
|  | Aerodynamics | [9 empty] | A05 - Auxiliary Elements
|  | Aerodynamics | [9 empty] | A05 - Auxiliary Elements
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
AE_A06_T001 | Plugs for Nosecone and Sidepods Made | Aerodynamics | 2026-10-16 | 2026-10-24 | Not Started |  | Ethan Gu | High |  | Nosecone and sidepod plugs |  | A06 - Sidepod
AE_A06_T002 | Manufacturing for Nosecone and Sidepod | Aerodynamics | 2026-10-24 | 2027-03-01 | Not Started |  | Ethan Gu | High |  | Manufactured nosecone and sidepod |  | A06 - Sidepod
|  | Aerodynamics | [9 empty] | A06 - Sidepod
|  | Aerodynamics | [9 empty] | A06 - Sidepod
|  | Aerodynamics | [9 empty] | A06 - Sidepod
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
AE_A07_T001 | Choose Radiatior Location Based on CFD | Aerodynamics | 2026-08-24 | 2026-09-24 | Not Started |  | Helen Laird | High |  | Radiator location selected |  | A07 - CFD
|  | Aerodynamics | [9 empty] | A07 - CFD
|  | Aerodynamics | [9 empty] | A07 - CFD
|  | Aerodynamics | [9 empty] | A07 - CFD
|  | Aerodynamics | [9 empty] | A07 - CFD
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Aerodynamics | [9 empty] | A08 - Other Aerodynamics
|  | Aerodynamics | [9 empty] | A08 - Other Aerodynamics
|  | Aerodynamics | [9 empty] | A08 - Other Aerodynamics
|  | Aerodynamics | [9 empty] | A08 - Other Aerodynamics
|  | Aerodynamics | [9 empty] | A08 - Other Aerodynamics

## ER Tasks
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
ER_A01_T001 | Ergo mockup points identified | Ergonomics | 2026-09-07 | 2026-09-30 | Not Started |  | James King | Critical |  |  |  | A01 - Ergonomics
ER_A01_T002 | Gather Whole System Driver Load Data Points | Ergonomics | 2026-09-01 | 2026-09-12 | Not Started |  | James King | High |  |  |  | A01 - Ergonomics
ER_A01_T003 | Put Linpots on ARG26 | Ergonomics | 2026-08-31 | 2026-08-31 | Planned |  | James King | High |  |  |  | A01 - Ergonomics
ER_A01_T004 | Get Driver Max Loads | Ergonomics | 2026-08-31 | 2026-09-02 | Not Started |  | James King | High |  |  |  | A01 - Ergonomics
A01 - Ergonomics
A01 - Ergonomics
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
ER_A02_T001 | Rack and Pinion Decided | Ergonomics | 2026-09-01 | 2026-09-30 | Not Started |  | James King | High |  |  |  | A02 - Steering
ER_A02_T002 | Insert Steering column | Ergonomics | 2027-01-14 | 2027-01-16 | Not Started |  | James King | Critical |  |  |  | A02 - Steering
|  | Ergonomics | [9 empty] | A02 - Steering
|  | Ergonomics | [9 empty] | A02 - Steering
|  | Ergonomics | [9 empty] | A02 - Steering
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
ER_A03_T001 | Pedal Ajustability Decided | Ergonomics | 2026-09-01 | 2026-09-12 | Not Started |  | Cameron Harvey | High |  |  |  | A03 - Pedals
ER_A03_T002 | Insert pedals | Ergonomics | 2027-01-15 | 2027-01-17 | Not Started |  | Cameron Harvey | Critical |  |  |  | A03 - Pedals
ER_A03_T003 | Determine Lockup force | Ergonomics |  |  |  |  | Cameron Harvey |  |  |  |  | A03 - Pedals
ER_A03_T004 | Order Tilton Prodcuts for pedals | Ergonomics |  |  |  |  | Cameron Harvey |  |  |  |  | A03 - Pedals
A03 - Pedals
A03 - Pedals
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
ER_A04_T001 | Drivers Molds Taken | Ergonomics | 2026-10-18 | 2026-10-24 | Not Started |  | James King | High |  |  |  | A04 - Seat
ER_A04_T002 | Driver Seat Scans in CAD | Ergonomics | 2026-10-25 | 2026-10-31 | Not Started |  | James King | High |  |  |  | A04 - Seat
ER_A04_T003 | Seat Upper Constraint Solution | Ergonomics | 2026-09-01 | 2026-09-30 | Not Started |  | James King | High |  |  |  | A04 - Seat
ER_A04_T004 | Make Plug for New Seat | Ergonomics | 2026-11-16 | 2026-11-27 | Not Started |  | James King | High |  |  |  | A04 - Seat
ER_A04_T005 | Layup New Driver Seat | Ergonomics | 2026-11-30 | 2026-12-11 | Not Started |  | James King | High |  |  |  | A04 - Seat
|  | Ergonomics | [9 empty] | A04 - Seat
|  | Ergonomics | [9 empty] | A04 - Seat
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
ER_A05_T001 | Order Firewall/Backups | Ergonomics | 2026-12-11 | 2026-12-16 | Not Started |  | James King | High |  |  |  | A05 - Firewall
ER_A05_T002 | Mount Firewall | Ergonomics | 2027-01-18 | 2027-01-18 | Not Started |  | James King | Critical |  |  |  | A05 - Firewall
|  | Ergonomics | [9 empty] | A05 - Firewall
|  | Ergonomics | [9 empty] | A05 - Firewall
|  | Ergonomics | [9 empty] | A05 - Firewall
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
ER_A06_T001 | Mount Head Restraint | Ergonomics | 2027-01-17 | 2027-01-18 | Not Started |  | James King | Critical |  |  |  | A06 - Head Restraint
ER_A06_T002 | Decide on mounting method of Head Restraint | Ergonomics | 2026-09-07 | 2026-09-30 | Not Started |  | James King | High |  |  |  | A06 - Head Restraint
A06 - Head Restraint
|  | Ergonomics | [9 empty] | A06 - Head Restraint
|  | Ergonomics | [9 empty] | A06 - Head Restraint
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Ergonomics | [9 empty] | A07 - Steering Wheel
|  | Ergonomics | [9 empty] | A07 - Steering Wheel
|  | Ergonomics | [9 empty] | A07 - Steering Wheel
|  | Ergonomics | [9 empty] | A07 - Steering Wheel
|  | Ergonomics | [9 empty] | A07 - Steering Wheel
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Ergonomics | [9 empty] | A08 - Other Ergonomics
|  | Ergonomics | [9 empty] | A08 - Other Ergonomics
|  | Ergonomics | [9 empty] | A08 - Other Ergonomics
|  | Ergonomics | [9 empty] | A08 - Other Ergonomics
|  | Ergonomics | [9 empty] | A08 - Other Ergonomics

## MO Tasks
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
MO_A01_T001 | Ordering Composite Materials | Monocoque | 2026-07-27 | 2026-08-14 | In Progress |  | Katherine Collard | Low |  |  |  | A01 - Monocoque
MO_A01_T002 |  | Monocoque |  |  | Not Started |  | Katherine Collard | Critical |  |  |  | A01 - Monocoque
MO_A01_T003 | Select foam and plug manufacturing process | Monocoque | 2026-08-30 | 2026-08-31 | Not Started |  | Katherine Collard | Critical |  | Documented foam/plug process and manufacturing location | Decide in-house vs. Woodward and old vs. new plugs. | A01 - Monocoque
MO_A01_T004 | Trial mold gel coat process | Monocoque | 2026-09-03 | 2026-09-03 | Not Started |  | Katherine Collard | Medium |  | Gel coat trial results |  | A01 - Monocoque
MO_A01_T005 | Pre-process plug with Dolphin Glaze or selected filler | Monocoque | 2026-09-07 | 2026-09-14 | Not Started |  | Katherine Collard | High |  | Prepared plug surface |  | A01 - Monocoque
MO_A01_T006 | Receive carbon materials | Monocoque | 2026-09-07 | 2026-09-07 | Not Started |  | Katherine Collard | Critical |  | Carbon available for layups |  | A01 - Monocoque
MO_A01_T007 | Print drilling and assembly jigs | Monocoque | 2026-10-22 | 2026-11-01 | Not Started |  | Katherine Collard | High |  | Printed jigs |  | A01 - Monocoque
MO_A01_T008 | Cut Delrin jig rods | Monocoque | 2026-10-23 | 2026-11-01 | Not Started |  | Katherine Collard | High |  | Cut Delrin rods |  | A01 - Monocoque
MO_A01_T009 | Source all jigging materials for monocoque holes | Monocoque | 2026-10-16 | 2026-10-24 | Not Started |  | Katherine Collard | Critical |  | Complete jigging material kit |  | A01 - Monocoque
MO_A01_T010 | Order drill-bushing stock | Monocoque | 2026-10-25 | 2026-10-25 | Not Started |  | Katherine Collard | High |  | Drill-bushing stock ordered |  | A01 - Monocoque
MO_A01_T011 | Drill monocoque holes using jigs | Monocoque | 2026-11-01 | 2026-11-03 | Not Started |  | Katherine Collard | Critical |  | Monocoque holes drilled to jig | Assumes continuous labor support. | A01 - Monocoque
MO_A01_T012 | Finish new-plug-to-post-process sequence | Monocoque | 2026-10-19 | 2026-11-04 | Not Started |  | Katherine Collard | Critical |  | Post-processed plug | Calendar indicates a 16-day duration. | A01 - Monocoque
MO_A01_T013 | Manufacture all drill bushings | Monocoque | 2026-11-06 | 2026-11-06 | Not Started |  | Katherine Collard | Critical |  | Completed drill bushings |  | A01 - Monocoque
MO_A01_T014 | Prepare all materials for mold manufacturing | Monocoque | 2026-11-07 | 2026-11-07 | Not Started |  | Katherine Collard | Critical |  | Mold manufacturing material kit |  | A01 - Monocoque
MO_A01_T015 | Complete puck development | Monocoque | 2026-11-08 | 2026-11-08 | Not Started |  | Katherine Collard | High |  | Puck design/manufacturing progress | Calendar note is tentative. | A01 - Monocoque
MO_A01_T016 | Finish plug preparation | Monocoque | 2026-11-11 | 2026-11-11 | Not Started |  | Katherine Collard | Critical |  | Plug ready for mold manufacture |  | A01 - Monocoque
MO_A01_T017 | Attempt wet-layup mold if ahead of schedule | Monocoque | 2026-11-14 | 2026-11-15 | Not Started |  | Katherine Collard | Low |  | Optional wet-layup mold trial | Stretch task; potentially both molds. | A01 - Monocoque
MO_A01_T018 | Release first mold | Monocoque | 2026-11-19 | 2026-11-19 | Not Started |  | Katherine Collard | High |  | First mold released |  | A01 - Monocoque
MO_A01_T019 | Prepare everything required for mold layup | Monocoque | 2026-11-30 | 2026-11-30 | Not Started |  | Katherine Collard | Critical |  | Mold layup readiness sign-off |  | A01 - Monocoque
MO_A01_T020 | Post-process molds | Monocoque | 2026-12-02 | 2026-12-02 | Not Started |  | Katherine Collard | High |  | Post-processed molds |  | A01 - Monocoque
MO_A01_T021 | Prepare molds, oven, carbon kits, and tooling for JanMan | Monocoque | 2027-01-04 | 2027-01-06 | Not Started |  | Katherine Collard | Critical |  | JanMan manufacturing readiness |  | A01 - Monocoque
MO_A01_T022 | Lay up first monocoque skin | Monocoque | 2027-01-07 | 2027-01-09 | Not Started |  | Katherine Collard | Critical |  | First skin laid up |  | A01 - Monocoque
MO_A01_T023 | Complete first cure and oven cycle | Monocoque | 2027-01-10 | 2027-01-10 | Not Started |  | Katherine Collard | Critical |  | First skin cured |  | A01 - Monocoque
MO_A01_T024 | Install and bond core | Monocoque | 2027-01-11 | 2027-01-13 | Not Started |  | Katherine Collard | Critical |  | Core installed | SES due date uncertainty noted on Jan. 12. | A01 - Monocoque
MO_A01_T025 | Lay up second monocoque skin | Monocoque | 2027-01-14 | 2027-01-16 | Not Started |  | Katherine Collard | Critical |  | Second skin laid up |  | A01 - Monocoque
MO_A01_T026 | Complete final cure | Monocoque | 2027-01-17 | 2027-01-17 | Not Started |  | Katherine Collard | Critical |  | Monocoque fully cured |  | A01 - Monocoque
MO_A01_T027 | Support powertrain integration | Monocoque | 2027-02-07 | 2027-02-07 | Not Started |  | Katherine Collard | High |  | Powertrain integration support complete |  | A01 - Monocoque
MO_A01_T028 | ANSYS 3 point bend test model | Monocoque | 2026-07-27 | 2026-08-07 | Not Started |  | Katherine Collard | Medium |  | model that can be easily tested for new data |  | A01 - Monocoque
MO_A01_T029 | ANSYS Twist Test | Monocoque | 2026-07-27 | 2026-08-24 | Not Started |  | Katherine Collard | Medium |  |  |  | A01 - Monocoque
MO_A01_T030 |  | Monocoque |  |  | Not Started |  | Katherine Collard | Critical |  | Validated ANSYS 3-point bend model/test plan | Calendar note asks whether testing is complete. | A01 - Monocoque
MO_A01_T031 |  | Monocoque |  |  | Not Started |  | Katherine Collard | Critical |  | Completed 3-point bend simulation set |  | A01 - Monocoque
|  | Monocoque | [9 empty] | A01 - Monocoque
|  | Monocoque | [9 empty] | A01 - Monocoque
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
MO_A02_T001 | Finalize monocoque CAD with points | Monocoque | 2026-09-01 | 2026-10-19 | Not Started |  | Katherine Collard | Medium |  | Updated monocoque CAD |  | A02 - MO Geometry
MO_A02_T002 | Update new monocoque CAD geometry | Monocoque | 2026-08-24 | 2026-09-30 | In Progress |  | Katherine Collard | Medium |  | Updated CAD geometry | No-redesign schedule assumes geometry changes remain limited. | A02 - MO Geometry
MO_A02_T003 | Lock monocoque CAD points | Monocoque | 2026-10-19 | 2026-10-19 | Not Started |  | Katherine Collard | Critical |  | Locked monocoque reference points |  | A02 - MO Geometry
|  | Monocoque | [9 empty] | A02 - MO Geometry
|  | Monocoque | [9 empty] | A02 - MO Geometry
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Monocoque | [9 empty] | A03 - Protective Structures
|  | Monocoque | [9 empty] | A03 - Protective Structures
|  | Monocoque | [9 empty] | A03 - Protective Structures
|  | Monocoque | [9 empty] | A03 - Protective Structures
|  | Monocoque | [9 empty] | A03 - Protective Structures
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
MO_A05_T001 | Ply Schedule Testing | Monocoque | [9 empty] | A05 - SES and Ply Schedules
MO_A05_T002 | Consult professional about laminates | Monocoque | 2026-08-11 | 2026-08-31 | Not Started |  |  | High |  | Material testing guidance and action items |  | A05 - SES and Ply Schedules
MO_A05_T003 | Run ANSYS twist-test ply schedule study | Monocoque | 2026-08-13 | 2026-09-11 | Not Started |  |  | Low |  | Twist-test ply schedule results |  | A05 - SES and Ply Schedules
MO_A05_T004 | Analyze panel test results | Monocoque | 2026-09-19 | 2026-09-19 | Not Started |  |  | Critical |  | Analyzed panel results and recommendations |  | A05 - SES and Ply Schedules
MO_A05_T005 | Complete additional test-panel round | Monocoque | 2026-09-27 | 2026-10-04 | Not Started |  |  | High |  | Additional panel test results | Calendar notes another panel round; one-week window assumed. | A05 - SES and Ply Schedules
MO_A05_T006 | Complete SES work session | Monocoque | 2026-11-05 | 2026-11-05 | Not Started |  |  | Critical |  | Updated SES package |  | A05 - SES and Ply Schedules
MO_A05_T007 | Continue test panels and SES documentation | Monocoque | 2026-11-09 | 2026-11-10 | Not Started |  |  | Critical |  | Updated SES test evidence |  | A05 - SES and Ply Schedules
MO_A05_T008 | Lock final ply schedules | Monocoque | 2026-09-30 | 2026-11-20 | Not Started |  |  | Critical |  | Released ply schedule |  | A05 - SES and Ply Schedules
MO_A05_T009 | Submit SES package | Monocoque | 2026-12-01 | 2026-12-01 | Not Started |  |  | Critical |  | Submitted SES package |  | A05 - SES and Ply Schedules
MO_A05_T010 | Test Panel Jigs and Elastic Modulus | Monocoque | 2026-08-17 | 2026-08-21 | Not Started |  |  | High |  | 1. Have 3 pt bending jig 2. Have an elastic modulus tested thats rules compliant 3. test T1100 4. Other testing jigs (1-2 must be done) |  | A05 - SES and Ply Schedules
|  | Monocoque | [9 empty] | A05 - SES and Ply Schedules
|  | Monocoque | [9 empty] | A05 - SES and Ply Schedules
|  | Monocoque | [9 empty] | A05 - SES and Ply Schedules
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Monocoque | [9 empty] | A06 - Other Monocoque
|  | Monocoque | [9 empty] | A06 - Other Monocoque
|  | Monocoque | [9 empty] | A06 - Other Monocoque
|  | Monocoque | [9 empty] | A06 - Other Monocoque
|  | Monocoque | [9 empty] | A06 - Other Monocoque

## SU Tasks
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
SU_A01_T001 | Run ARG26 CG Test | Suspension | 2026-08-31 | 2026-09-05 | Not Started |  | Davis Rattanavijai |  |  |  | Very very valuable information | A01 - Suspension
SU_A01_T002 | GRIND KINEMATIC POINTS | Suspension | 2026-09-06 | 2026-09-13 | Not Started |  | Davis Rattanavijai |  | SU_A01_T003 |  |  | A01 - Suspension
SU_A01_T003 | Gather Design Necessary Car Data | Suspension | 2026-09-05 | 2026-09-19 | Not Started |  | Davis Rattanavijai |  |  |  | Max lateral, longitudinal acceleration and more to come | A01 - Suspension
SU_A01_T004 | test task | Suspension | [9 empty] | A01 - Suspension
|  | Suspension | [9 empty] | A01 - Suspension
|  | Suspension | [9 empty] | A01 - Suspension
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
SU_A02_T001 | Links manufacturing | Suspension | 2026-11-01 | 2027-01-15 | Not Started |  | Daniel Wtorkowski |  |  |  |  | A02 - Links
SU_A02_T002 | Calculate Link Dimensions (Length, OD and Wall thickness) | Suspension |  |  | Not Started |  | Daniel Wtorkowski | High |  |  |  | A02 - Links
SU_A02_T003 | First Round CAD of links and adapters | Suspension |  |  | Not Started |  | Daniel Wtorkowski | Medium | SU_A01_T002 |  |  | A02 - Links
SU_A02_T004 | Optimize Upper Adapter Geometry | Suspension |  |  | Not Started |  | Daniel Wtorkowski | Medium | SU_A02_T003 |  |  | A02 - Links
SU_A02_T005 | Order rod ends, bearings, tube stock from McMaster | Suspension |  |  | Not Started |  | Daniel Wtorkowski | Medium |  |  |  | A02 - Links
SU_A02_T006 | Order adapters from ZTL | Suspension |  |  | Not Started |  | Daniel Wtorkowski | High |  |  |  | A02 - Links
SU_A02_T007 | Machine Inserts | Suspension |  |  | Not Started |  | Daniel Wtorkowski | High |  |  |  | A02 - Links
SU_A02_T008 | Manufacture push links for strain gauge installation as well as spares | Suspension |  |  | Not Started |  | Daniel Wtorkowski | High |  |  |  | A02 - Links
|  | Suspension | [9 empty] | A02 - Links
|  | Suspension | [9 empty] | A02 - Links
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
SU_A03_T001 | Clevises manufacturing | Suspension | 2026-11-01 | 2027-01-15 | Not Started | [6 empty] | A03 - Clevises
SU_A03_T002 | Devcon Clevises | Suspension | 2027-01-21 | 2027-01-22 | Not Started | [6 empty] | A03 - Clevises
|  | Suspension | [9 empty] | A03 - Clevises
|  | Suspension | [9 empty] | A03 - Clevises
|  | Suspension | [9 empty] | A03 - Clevises
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
SU_A04_T001 | Rockers outsourced | Suspension | 2026-11-01 | 2027-01-15 | Not Started |  | Aarian Mepani |  |  |  |  | A04 - Rockers
|  | Suspension | [9 empty] | A04 - Rockers
|  | Suspension | [9 empty] | A04 - Rockers
|  | Suspension | [9 empty] | A04 - Rockers
|  | Suspension | [9 empty] | A04 - Rockers
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
SU_A05_T001 | Lock down ARB architecture | Suspension |  | 2026-09-21 | Not Started |  | Alice Jones | High |  | Decide on ARB front and rear architecture |  | A05 - Anti-Roll
SU_A05_T002 | First ARB CAD pass | Suspension |  | 2026-09-28 | Not Started |  | Alice Jones | Medium |  | Have an initial CAD assembly ready for PDR |  | A05 - Anti-Roll
SU_A05_T003 | Refine torsion bar sizing, Optimise blade geometry, Validate stiffness targets | Suspension | 2026-09-28 | 2026-10-24 | Not Started |  | Alice Jones | Medium |  |  |  | A05 - Anti-Roll
SU_A05_T004 | Design ARB Mounts and Adapters | Suspension | 2026-10-10 | 2026-10-24 | Not Started |  | Alice Jones | Medium |  |  |  | A05 - Anti-Roll
SU_A05_T005 | ARB CAD Freeze | Suspension | 2026-10-24 | 2026-11-05 | Not Started |  | Alice Jones | Medium |  |  | Straight After FDR | A05 - Anti-Roll
SU_A05_T006 | Place orders for outsourced ARB components | Suspension | 2026-11-05 | 2026-11-08 | Not Started |  | Alice Jones | Medium |  |  |  | A05 - Anti-Roll
SU_A05_T007 | Manufacture 50% of in-house ARB components | Suspension | 2026-11-08 | 2026-12-13 | Not Started |  | Alice Jones | Medium |  |  |  | A05 - Anti-Roll
SU_A05_T008 | Complete remaining ARB machining | Suspension | 2027-01-01 | 2027-01-15 | Not Started |  | Alice Jones | Medium |  |  |  | A05 - Anti-Roll
SU_A05_T009 | Assemble complete ARB | Suspension | 2027-01-15 | 2027-01-18 | Not Started |  | Alice Jones | Medium |  |  |  | A05 - Anti-Roll
SU_A05_T010 | Integrate ARB onto chassis with other suspension components | Suspension | 2027-01-18 | 2027-01-24 | Not Started |  | Alice Jones | Medium |  |  |  | A05 - Anti-Roll
|  | Suspension | [9 empty] | A05 - Anti-Roll
|  | Suspension | [9 empty] | A05 - Anti-Roll
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Suspension | [9 empty] | A08 - Jig Plate
|  | Suspension | [9 empty] | A08 - Jig Plate
|  | Suspension | [9 empty] | A08 - Jig Plate
|  | Suspension | [9 empty] | A08 - Jig Plate
|  | Suspension | [9 empty] | A08 - Jig Plate
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Suspension | [9 empty] | A09 - Other Suspension
|  | Suspension | [9 empty] | A09 - Other Suspension
|  | Suspension | [9 empty] | A09 - Other Suspension
|  | Suspension | [9 empty] | A09 - Other Suspension
|  | Suspension | [9 empty] | A09 - Other Suspension

## UN Tasks
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Unsprung | [9 empty] | A01 - Unsprung
|  | Unsprung | [9 empty] | A01 - Unsprung
|  | Unsprung | [9 empty] | A01 - Unsprung
|  | Unsprung | [9 empty] | A01 - Unsprung
|  | Unsprung | [9 empty] | A01 - Unsprung
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Unsprung | [9 empty] | A02 - Hubs and Uprights
|  | Unsprung | [9 empty] | A02 - Hubs and Uprights
|  | Unsprung | [9 empty] | A02 - Hubs and Uprights
|  | Unsprung | [9 empty] | A02 - Hubs and Uprights
|  | Unsprung | [9 empty] | A02 - Hubs and Uprights
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Unsprung | [9 empty] | A03 - Brakes
|  | Unsprung | [9 empty] | A03 - Brakes
|  | Unsprung | [9 empty] | A03 - Brakes
|  | Unsprung | [9 empty] | A03 - Brakes
|  | Unsprung | [9 empty] | A03 - Brakes
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Unsprung | [9 empty] | A04 - Gearbox
|  | Unsprung | [9 empty] | A04 - Gearbox
|  | Unsprung | [9 empty] | A04 - Gearbox
|  | Unsprung | [9 empty] | A04 - Gearbox
|  | Unsprung | [9 empty] | A04 - Gearbox
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Unsprung | [9 empty] | A05 - Other Unsprung
|  | Unsprung | [9 empty] | A05 - Other Unsprung
|  | Unsprung | [9 empty] | A05 - Other Unsprung
|  | Unsprung | [9 empty] | A05 - Other Unsprung
|  | Unsprung | [9 empty] | A05 - Other Unsprung

## BU Tasks
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
BU_A01_T001 | Professonally Wrap Car | Business | 2027-02-12 | 2027-02-15 | Not Started |  |  | High |  |  |  | A01 - Business
BU_A01_T003 | Finalize Comp Documents | Business | 2027-05-01 | 2027-05-05 | [7 empty] | A01 - Business
|  | Business | [9 empty] | A01 - Business
|  | Business | [9 empty] | A01 - Business
|  | Business | [9 empty] | A01 - Business
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
BU_A02_T001 | Publish Purchasing sheet | Business | 2026-08-28 | 2026-08-30 | In Progress |  |  | High |  |  |  | A02 - Purchasing
|  | Business | [9 empty] | A02 - Purchasing
|  | Business | [9 empty] | A02 - Purchasing
|  | Business | [9 empty] | A02 - Purchasing
|  | Business | [9 empty] | A02 - Purchasing
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
BU_A03_T001 | Upperclassmen Delibs 1 | Business | 2026-09-08 | 2026-09-08 | Not Started | [6 empty] | A03 - Recruitment
BU_A03_T002 | Upperclassmen interviews | Business | 2026-09-06 | 2026-09-14 | [7 empty] | A03 - Recruitment
BU_A03_T003 | Project Team Fest | Business |  | 2026-09-01 | Complete | [6 empty] | A03 - Recruitment
BU_A03_T004 | Info Session 1 | Business |  | 2026-09-02 | Complete | [6 empty] | A03 - Recruitment
BU_A03_T005 | Info Session 2 | Business |  | 2026-09-15 | [7 empty] | A03 - Recruitment
BU_A03_T006 | Info Session 3 | Business |  | 2026-09-21 | [7 empty] | A03 - Recruitment
BU_A03_T007 | Info Session 4 | Business |  | 2026-10-07 | [7 empty] | A03 - Recruitment
BU_A03_T008 | First Year Delibs 1 | Business | 2026-10-17 | 2026-10-18 | [7 empty] | A03 - Recruitment
BU_A03_T009 | Upperclassmen Final Delibs | Business | 2026-10-12 | 2026-10-13 | [7 empty] | A03 - Recruitment
BU_A03_T010 | First Year Interviews | Business | 2026-10-20 | 2026-10-27 | [7 empty] | A03 - Recruitment
BU_A03_T011 | First Year Final Delibs | Business | 2026-10-31 | 2026-11-01 | [7 empty] | A03 - Recruitment
|  | Business | [9 empty] | A03 - Recruitment
|  | Business | [9 empty] | A03 - Recruitment
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Business | [9 empty] | A04 - Business Presentations
|  | Business | [9 empty] | A04 - Business Presentations
|  | Business | [9 empty] | A04 - Business Presentations
|  | Business | [9 empty] | A04 - Business Presentations
|  | Business | [9 empty] | A04 - Business Presentations
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Business | [9 empty] | A05 - Fundraising, Sponsors
|  | Business | [9 empty] | A05 - Fundraising, Sponsors
|  | Business | [9 empty] | A05 - Fundraising, Sponsors
|  | Business | [9 empty] | A05 - Fundraising, Sponsors
|  | Business | [9 empty] | A05 - Fundraising, Sponsors
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
BU_A06_T001 | Finalize website | Business | 2026-08-24 | 2026-08-27 | Complete |  | Sayee Edekar | Low |  |  |  | A06 - Website
|  | Business | [9 empty] | A06 - Website
|  | Business | [9 empty] | A06 - Website
|  | Business | [9 empty] | A06 - Website
|  | Business | [9 empty] | A06 - Website
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Business | [9 empty] | A07 - Social Media
|  | Business | [9 empty] | A07 - Social Media
|  | Business | [9 empty] | A07 - Social Media
|  | Business | [9 empty] | A07 - Social Media
|  | Business | [9 empty] | A07 - Social Media
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Business | [9 empty] | A08 - Merch
|  | Business | [9 empty] | A08 - Merch
|  | Business | [9 empty] | A08 - Merch
|  | Business | [9 empty] | A08 - Merch
|  | Business | [9 empty] | A08 - Merch
ID | Task | Subteam | Start | Due | Status | Milestone | Owner | Priority | Dependencies | Deliverables | Notes | Part Design
|  | Business | [9 empty] | A09 - Other Business
|  | Business | [9 empty] | A09 - Other Business
|  | Business | [9 empty] | A09 - Other Business
|  | Business | [9 empty] | A09 - Other Business
|  | Business | [9 empty] | A09 - Other Business